## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | DARJEELING | Kurseong | Neorakhola W/S & Mtc.Div. | PWS Scheme for Shiva Khola Forest under Kurseong Sub - Division, PHED, GTA | SM/11396 | New | Material Requisition To Resource Division |  |  | RTOR000225/2022-2023 | 2566/NKWSMD | 17/02/2023 | 17/02/2023 | Resource Division | 0.65 | 0 | 0 | 0
2 | DARJEELING | Kurseong | Neorakhola W/S & Mtc.Div. | PWS Scheme for Shiva Khola Forest under Kurseong Sub - Division, PHED, GTA | SM/11396 | New | SURFACE WATER BASED SHIVAKHOLA FOREST PAGLA JHORA PIPED WATER SUPPLY SCHEME TO ACCOMMODATE FHTC IN KURSEONG BLOCK WITH IN DARJEELING DISTRICT UNDER KURSEONG DIVISION, P.H.E.D-GTA. |  |  | ORD/000284/2022-2023 | 2082/NKWSMD | 10/01/2023 | 09/07/2023 | SWAD CONSTRUCTION | 168.21 | 0 | 0 | 100
3 | DARJEELING | Kurseong | Neorakhola W/S & Mtc.Div. | PWS Scheme for Shiva Khola Forest under Kurseong Sub - Division, PHED, GTA | SM/11396 | New | ADDITIONAL WORK FOR SUPPLEMENTARY ITEMS IN ONGOING SHIVKHOLA FOREST PAGLAJHORA PIPED WATER SUPPLY SCHEMES UNDER KURSEONG DIVISION, PHED, GTA. |  |  | ORD/000013/2025-2026 | 499/NKWSMD | 09/04/2025 | 08/07/2025 | SWAD CONSTRUCTION | 55.85 | 0 | 0 | 0
Total | [13 empty] | 224.72 | 0 | 0