## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | DARJEELING | Kurseong | Neorakhola W/S & Mtc.Div. | PWS Scheme for Punkhabari under Kurseong Sub - Division, PHED, GTA. | SM/11398 | New | SURFACE WATER BASED PUNKHABARI PWSS TO ACCOMMODATE FHTC IN KURSEONG BLOCK WITHIN DARJEELING DISTRICT UNDER KURSEONG DIVISION, P.H.E.D-GTA |  |  | ORD/000300/2022-2023 | 2351/NKWSMD | 01/02/2023 | 22/12/2026 | SHAKTI CONSTRUCTION | 298.42 | 146.86 | 49.21 | 100
2 | DARJEELING | Kurseong | Neorakhola W/S & Mtc.Div. | PWS Scheme for Punkhabari under Kurseong Sub - Division, PHED, GTA. | SM/11398 | New | Material Requisition To Resource Division |  |  | RTOR000212/2022-2023 | 2560/NKWSMD | 17/02/2023 | 17/02/2023 | Resource Division | 1.39 | 0 | 0 | 0
3 | DARJEELING | Kurseong | Neorakhola W/S & Mtc.Div. | PWS Scheme for Punkhabari under Kurseong Sub - Division, PHED, GTA. | SM/11398 | New | Augmentation of Surface Water Based Piped Water Supply Scheme to accommodate Functional Household Tap Connection (FHTC) in Kurseong Block in Functional Household Tap Connection in Kurseong Block within Darjeeling District under Kurseong Division, PHED-G.T.A. |  |  | ORD/000030/2024-2025 | 1167/NKWSMD | 04/07/2024 | 29/07/2025 | SHAKTI CONSTRUCTION | 36.03 | 0 | 0 | 100
Total | [13 empty] | 335.84 | 146.86 | 43.73