## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | DARJEELING | Kurseong | Neorakhola W/S & Mtc.Div. | PWS Scheme for Lower Mamring under Kurseong Sub - Division, PHED, GTA | SM/11399 | New | Material Requisition To Resource Division |  |  | RTOR000044/2023-2024 | 321/NKWSMD | 24/05/2023 | 24/05/2023 | Resource Division | 0.69 | 0 | 0 | 0
2 | DARJEELING | Kurseong | Neorakhola W/S & Mtc.Div. | PWS Scheme for Lower Mamring under Kurseong Sub - Division, PHED, GTA | SM/11399 | New | Surface water based Lower Mamring Khasmahal in Kurseong Block within Darjeeling District. |  |  | ORD/000043/2023-2024 | 187/NKWSMD | 04/05/2023 | 24/03/2025 | PREM CHANDRA RAI | 356.26 | 192.19 | 53.94 | 85
3 | DARJEELING | Kurseong | Neorakhola W/S & Mtc.Div. | PWS Scheme for Lower Mamring under Kurseong Sub - Division, PHED, GTA | SM/11399 | New | ADDITIONAL WORK FOR PIPED WATER SUPPLY SCHEME FOR LOWER MAMRING UNDER KURSEONG SUB- DIVISION, P.H.E.D-GTA. |  |  | ORD/000066/2025-2026 | 999/NKWSMD | 09/07/2025 | 05/01/2026 | ANUGRAH CONSTRUCTION | 146.56 | 0 | 0 | 0
Total | [13 empty] | 503.52 | 192.19 | 38.17