## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | DARJEELING | Jorebunglow Sukiapokhri | Neorakhola W/S & Mtc.Div. | GRAVITY BASED WATER SUPPLY SCHEME FOR MOLATEY AND AVONGROVE TEA GARDEN PWSS | SM/11854 | New | Material Requisition To Resource Division |  |  | RTOR000112/2022-2023 | 1889/NKWSMD | 15/12/2022 | 15/12/2022 | Resource Division | 4.41 | 0 | 0 | 0
2 | DARJEELING | Jorebunglow Sukiapokhri | Neorakhola W/S & Mtc.Div. | GRAVITY BASED WATER SUPPLY SCHEME FOR MOLATEY AND AVONGROVE TEA GARDEN PWSS | SM/11854 | New | Material Requisition To Resource Division |  |  | RTOR000171/2022-2023 | 2572/NKWSMD | 17/02/2023 | 17/02/2023 | Resource Division | 4.41 | 0 | 0 | 0
3 | DARJEELING | Jorebunglow Sukiapokhri | Neorakhola W/S & Mtc.Div. | GRAVITY BASED WATER SUPPLY SCHEME FOR MOLATEY AND AVONGROVE TEA GARDEN PWSS | SM/11854 | New | WATER SUPPLY SCHEME FOR MOLATEY AND AVONGRAVE TEA GARDEN PWSS IN JOREBUNGLOW SUKIAPOKHRI UNDER DARJEELING DISTRICT | Assistant Engineer |  | ORD/000235/2022-2023 | 1452/NKWSMD | 29/09/2022 | 26/01/2025 | SHAKTI CONSTRUCTION | 926.69 | 779.09 | 84.07 | 99
Total | [13 empty] | 935.51 | 779.09 | 83.28