## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | DARJEELING | Jorebunglow Sukiapokhri | Neorakhola W/S & Mtc.Div. | GRAVITY BASED WATER SUPPLY SCHEME FOR SUKHIYAPOKHRI PWSS | SM/11855 | New | Additional Work for Providing FHTC under Jal Jeevan Mission for balance Household at Maneybhanjang Forest Village Gram Panchayat: Sukhia Simana Block: Jorebunglow Sukhiapokhri. |  |  | ORD/000200/2023-2024 | 1082/NKWSMD | 19/09/2023 | 18/12/2023 | MOHAN MUKHIA | 55.31 | 0 | 0 | 70
2 | DARJEELING | Jorebunglow Sukiapokhri | Neorakhola W/S & Mtc.Div. | GRAVITY BASED WATER SUPPLY SCHEME FOR SUKHIYAPOKHRI PWSS | SM/11855 | New | WATER SUPPLY SCHEME FOR SUKHIA POKHARI PIPED WATER SUPPLY SCHEME IN JOREBUNGLOW BLOCK UNDER DARJEELING DISTRICT. |  |  | ORD/000253/2022-2023 | 1525/NKWSMD | 17/10/2022 | 14/06/2023 | SUMAN PRADHAN | 317.2 | 198.16 | 62.47 | 100
Total | [13 empty] | 372.52 | 198.16 | 53.19