## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | DARJEELING | Jorebunglow Sukiapokhri | Neorakhola W/S & Mtc.Div. | GRAVITY BASED WATER SUPPLY SCHEME FOR PULUNGDUNG TEA ESTATE PWSS BLOCK- JORE BUNGALOW- SUKHIYAPOKHRI, DISTRICT- DARJEELING | SM/11856 | New | PULUNGDONG TEA ESTATE VILLAGE WATER SUPPLY SCHEME UNDER JOREBUNGLOW SUKHIAPOKHARI BLOCK. |  |  | ORD/000078/2023-2024 | 677/NKWSMD | 12/07/2023 | 08/01/2024 | SATHI CONSTRUCTION COMPANY | 239.24 | 193.81 | 81.01 | 100
2 | DARJEELING | Jorebunglow Sukiapokhri | Neorakhola W/S & Mtc.Div. | GRAVITY BASED WATER SUPPLY SCHEME FOR PULUNGDUNG TEA ESTATE PWSS BLOCK- JORE BUNGALOW- SUKHIYAPOKHRI, DISTRICT- DARJEELING | SM/11856 | New | Material Requisition To Resource Division |  |  | RTOR000067/2023-2024 | 762/NKWSMD | 19/07/2023 | 19/07/2023 | Resource Division | 0.62 | 0 | 0 | 0
3 | DARJEELING | Jorebunglow Sukiapokhri | Neorakhola W/S & Mtc.Div. | GRAVITY BASED WATER SUPPLY SCHEME FOR PULUNGDUNG TEA ESTATE PWSS BLOCK- JORE BUNGALOW- SUKHIYAPOKHRI, DISTRICT- DARJEELING | SM/11856 | New | ADDITIONAL WORK FOR PULUNGDUNG TEA ESTATE PIPED WATER SUPPLY SCHEME UNDER BLOCK-JOREBUNGLOW SUKIAPOKRI DISTRICT-DARJEELING. |  |  | ORD/000146/2024-2025 | 2349/NKWSMD | 19/12/2024 | 19/03/2025 | SATHI CONSTRUCTION COMPANY | 47.86 | 0 | 0 | 0
Total | [13 empty] | 287.72 | 193.81 | 67.36