## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | DARJEELING | Jorebunglow Sukiapokhri | Neorakhola W/S & Mtc.Div. | GRAVITY BASED WATER SUPPLY SCHEME FOR RANGAROONG TEA GARDEN PWSS, BLOCK: JORE BUNGALOW-SUKHIAPOKHRI, DISTRICT: DARJEELING. | SM/11889 | New | Material Requisition To Resource Division |  |  | RTOR000115/2022-2023 | 1892/NKWSMD | 15/12/2022 |  | Resource Division | 1.64 | 0 | 0 | 0
2 | DARJEELING | Jorebunglow Sukiapokhri | Neorakhola W/S & Mtc.Div. | GRAVITY BASED WATER SUPPLY SCHEME FOR RANGAROONG TEA GARDEN PWSS, BLOCK: JORE BUNGALOW-SUKHIAPOKHRI, DISTRICT: DARJEELING. | SM/11889 | New | Material Requisition To Resource Division |  |  | RTOR000174/2022-2023 | 2611/NKWSMD | 17/02/2023 |  | Resource Division | 1.64 | 0 | 0 | 0
3 | DARJEELING | Jorebunglow Sukiapokhri | Neorakhola W/S & Mtc.Div. | GRAVITY BASED WATER SUPPLY SCHEME FOR RANGAROONG TEA GARDEN PWSS, BLOCK: JORE BUNGALOW-SUKHIAPOKHRI, DISTRICT: DARJEELING. | SM/11889 | New | Additional work for Rageroong Tea Estate for water supply scheme under Darjeeling Division,PHED-GTA. | Assistant Engineer | Junior Engineer-V | ORD/000121/2023-2024 | 862/NKWSMD | 31/07/2023 | 29/09/2023 | KUNCHAN JUNGA ENTERPRISES | 30.33 | 0 | 0 | 0
4 | DARJEELING | Jorebunglow Sukiapokhri | Neorakhola W/S & Mtc.Div. | GRAVITY BASED WATER SUPPLY SCHEME FOR RANGAROONG TEA GARDEN PWSS, BLOCK: JORE BUNGALOW-SUKHIAPOKHRI, DISTRICT: DARJEELING. | SM/11889 | New | WATER SUPPLY SCHEME FOR RANGAROONG TEA GARDEN PWSS, BLOCK: JORE BUNGALOW-SUKHIAPOKHRI, DISTRICT: DARJEELING.(TSM/012508) |  |  | ORD/000251/2022-2023 | 1529/NKWSMD | 18/10/2022 | 16/04/2023 | KUNCHAN JUNGA ENTERPRISES | 272.77 | 212.34 | 77.84 | 70
Total | [13 empty] | 306.38 | 212.34 | 69.3