## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | DARJEELING | Jorebunglow Sukiapokhri | Neorakhola W/S & Mtc.Div. | GRAVITY BASED WATER SUPPLY SCHEME FOR TURZUM TEA GARDEN PWSS. BLOCK- JORE BUNGALOW- SUKHIAPOKHRI, DISTRICT DARJEELING | SM/11890 | New | Material Requisition To Resource Division |  |  | RTOR000111/2022-2023 | 1888/NKWSMD | 15/12/2022 | 15/12/2022 | Resource Division | 3.24 | 0 | 0 | 0
2 | DARJEELING | Jorebunglow Sukiapokhri | Neorakhola W/S & Mtc.Div. | GRAVITY BASED WATER SUPPLY SCHEME FOR TURZUM TEA GARDEN PWSS. BLOCK- JORE BUNGALOW- SUKHIAPOKHRI, DISTRICT DARJEELING | SM/11890 | New | Material Requisition To Resource Division |  |  | RTOR000170/2022-2023 | 2607/NKWSMD | 17/02/2023 | 17/02/2023 | Resource Division | 3.24 | 0 | 0 | 0
3 | DARJEELING | Jorebunglow Sukiapokhri | Neorakhola W/S & Mtc.Div. | GRAVITY BASED WATER SUPPLY SCHEME FOR TURZUM TEA GARDEN PWSS. BLOCK- JORE BUNGALOW- SUKHIAPOKHRI, DISTRICT DARJEELING | SM/11890 | New | GRAVITY BASED WATER SUPPLY SCHEME FOR TURZUN TEA GARDEN PWSS IN JOREBUNGLOW SUKIAPOKHARI BLOCK UNDER DARJEELING DISTRICT. |  |  | ORD/000233/2022-2023 | 1449/NKWSMD | 29/09/2022 | 26/01/2025 | SRINIWAS AGARWAL | 748.35 | 655.64 | 87.61 | 99
Total | [13 empty] | 754.83 | 655.64 | 86.86