## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | DARJEELING | Kurseong | Neorakhola W/S & Mtc.Div. | PWS Scheme for Rohini Tea Garden | SM/11938 | New | Material Requisition To Resource Division |  |  | RTOR000152/2022-2023 | 2072/NKWSMD | 05/01/2023 |  | Resource Division | 8.37 | 0 | 0 | 0
2 | DARJEELING | Kurseong | Neorakhola W/S & Mtc.Div. | PWS Scheme for Rohini Tea Garden | SM/11938 | New | Material Requisition To Resource Division |  |  | RTOR000043/2023-2024 | 322/NKWSMD | 24/05/2023 |  | Resource Division | 1.69 | 0 | 0 | 0
3 | DARJEELING | Kurseong | Neorakhola W/S & Mtc.Div. | PWS Scheme for Rohini Tea Garden | SM/11938 | New | SURFACE WATER BASED ROHINI TEA GARDEN PIPED WATER SUPPLY SCHEME TO ACCOMODTE FHTC IN KURSOENG BLOCK WITHIN DARJEELING DISTRICT UNDER KURSEONG DIVISION, PHE DTE. |  |  | ORD/000011/2023-2024 | 100/NKWSMD | 28/04/2023 | 25/10/2023 | RUKMANI ENGINEERING WORKS | 324.1 | 127.93 | 39.47 | 50
Total | [13 empty] | 334.16 | 127.93 | 38.28