## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | DARJEELING | Kurseong | Neorakhola W/S & Mtc.Div. | WATER SUPPLY SCHEME FOR SPRING SIDI TEA GARDEN PWSS IN KURSEONG BLOCK UNDER DARJEELING DISTRICT. | SM/11942 | New | Material Requisition To Resource Division |  |  | RTOR000134/2023-2024 | 700/NKWSMD | 22/03/2024 | 22/03/2024 | Resource Division | 1.52 | 0 | 0 | 0
2 | DARJEELING | Kurseong | Neorakhola W/S & Mtc.Div. | WATER SUPPLY SCHEME FOR SPRING SIDI TEA GARDEN PWSS IN KURSEONG BLOCK UNDER DARJEELING DISTRICT. | SM/11942 | New | ADDITIONAL WORK FOR SUPPLEMENTARY ITEMS IN ONGOING SPRING SIDI PIPED WATER SUPPLY SCHEMES UNDER KURSEONG DIVISION, PHED, GTA |  |  | ORD/000053/2025-2026 | 776/NKWSMD | 28/05/2025 | 27/07/2025 | HIMALAYAN CONSTRUCTION | 11.53 | 0 | 0 | 0
3 | DARJEELING | Kurseong | Neorakhola W/S & Mtc.Div. | WATER SUPPLY SCHEME FOR SPRING SIDI TEA GARDEN PWSS IN KURSEONG BLOCK UNDER DARJEELING DISTRICT. | SM/11942 | New | Water Supply Scheme for Spring Sidi Tea Garden village Piped Water Supply Scheme In Kurseong Under Darjeeling District. |  |  | ORD/000320/2022-2023 | 2644/NKWSMD | 24/02/2023 | 04/04/2025 | HIMALAYAN CONSTRUCTION | 217.45 | 105.39 | 48.47 | 100
Total | [13 empty] | 230.5 | 105.39 | 45.72