## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | DARJEELING | Jorebunglow Sukiapokhri | Neorakhola W/S & Mtc.Div. | GRAVITY BASED WATER SUPPLY SCHEME FOR POKHARIBONG KHASMAHAL PWSS IN JORE BUNGLOW SUKHIAPIOKHARI BLOCK UNDER DARJEELING DISTRICT. | SM/11944 | New | WATER SUPPLY SCHEME FOR POKHRIBONG KHASMAHAL PWSS IN BLOCK JOREBUNGLOW SUKIAPOKRI UNDER DISTRICT DARJEELING. |  |  | ORD/000256/2022-2023 | 1619/NKWSMD | 03/11/2022 | 02/05/2023 | YAMA CONSTRUCTIONS LLP | 897.18 | 877.56 | 97.81 | 0
2 | DARJEELING | Jorebunglow Sukiapokhri | Neorakhola W/S & Mtc.Div. | GRAVITY BASED WATER SUPPLY SCHEME FOR POKHARIBONG KHASMAHAL PWSS IN JORE BUNGLOW SUKHIAPIOKHARI BLOCK UNDER DARJEELING DISTRICT. | SM/11944 | New | Material Requisition To Resource Division |  |  | RTOR000101/2023-2024 | 964/NKWSMD | 21/08/2023 | 21/08/2023 | Resource Division | 3.58 | 0 | 0 | 0
3 | DARJEELING | Jorebunglow Sukiapokhri | Neorakhola W/S & Mtc.Div. | GRAVITY BASED WATER SUPPLY SCHEME FOR POKHARIBONG KHASMAHAL PWSS IN JORE BUNGLOW SUKHIAPIOKHARI BLOCK UNDER DARJEELING DISTRICT. | SM/11944 | New | Supply and erection of scheme information board made of 50X50X6 mm. M.S. angle frame 6¿00¿X4¿00¿ size at a height over 1.5M. over ground including ties and bracing made of 32X32X6 mm. M.S. Angle and legs(50X50X6mm) are embedded at a depth of 600 mm. and to be fixed in Cement Concrete (1:2:4) footing size 250X250X600 mm. underground. The board for display to be made on latex venyle print as per standard format given from department to be pasted over M.S. sheet (size-6¿X4¿) including carriage, loading, unloading at different sites for different JJM works under Darjeeling Division-I, P.H.E.D., GTA | Assistant Engineer II |  | ORD/000261/2023-2024 | 159/AE-II/NKWSMD | 10/01/2024 | 25/01/2024 | MADAN KUMAR CHHETRI | 23.94 | 0 | 0 | 100
4 | DARJEELING | Jorebunglow Sukiapokhri | Neorakhola W/S & Mtc.Div. | GRAVITY BASED WATER SUPPLY SCHEME FOR POKHARIBONG KHASMAHAL PWSS IN JORE BUNGLOW SUKHIAPIOKHARI BLOCK UNDER DARJEELING DISTRICT. | SM/11944 | New | Additional work piped water supply scheme for Pokhriabong Busty No. 5 under Jal Jiwan Mission and Jal Swapno Programme. |  |  | ORD/000179/2023-2024 | 940/NKWSMD | 16/08/2023 | 07/01/2025 | RISHI KESH THAKURI | 12.62 | 0 | 0 | 100
Total | [13 empty] | 937.32 | 877.56 | 93.62