## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | DARJEELING | Jorebunglow Sukiapokhri | Neorakhola W/S & Mtc.Div. | GRAVITY BASED WATER SUPPLY SCHEME FOR CHAMU TEA GARDEN PWSS, BLOCK- JORE BUNGLOW, SUKHIAPOKHRI, DISTRICT- DARJEELING. | SM/11952 | New | WATER SUPPLY SCHEME FOR CHAMU TEA GARDEN PWSS IN JOREBUNGLOW SUKIAPAKHRI BLOCK UNDER DARGEELING DISTRICT. |  |  | ORD/000257/2022-2023 | 1620/NKWSMD | 03/11/2022 | 01/05/2024 | GARGO TRADERS | 874.98 | 860.66 | 98.36 | 90
2 | DARJEELING | Jorebunglow Sukiapokhri | Neorakhola W/S & Mtc.Div. | GRAVITY BASED WATER SUPPLY SCHEME FOR CHAMU TEA GARDEN PWSS, BLOCK- JORE BUNGLOW, SUKHIAPOKHRI, DISTRICT- DARJEELING. | SM/11952 | New | Material Requisition To Resource Division |  |  | RTOR000116/2022-2023 | 1893/NKWSMD | 15/12/2022 | 15/12/2022 | Resource Division | 4.72 | 0 | 0 | 0
3 | DARJEELING | Jorebunglow Sukiapokhri | Neorakhola W/S & Mtc.Div. | GRAVITY BASED WATER SUPPLY SCHEME FOR CHAMU TEA GARDEN PWSS, BLOCK- JORE BUNGLOW, SUKHIAPOKHRI, DISTRICT- DARJEELING. | SM/11952 | New | Material Requisition To Resource Division |  |  | RTOR000175/2022-2023 | 2573/NKWSMD | 17/02/2023 | 17/02/2023 | Resource Division | 4.72 | 0 | 0 | 0
Total | [13 empty] | 884.41 | 860.66 | 97.31