## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | DARJEELING | Jorebunglow Sukiapokhri | Neorakhola W/S & Mtc.Div. | GRAVITY BASED WATER SUPPLY SCHEME FOR TAMSANG TEA GARDEN PWSS, BLOCK : JORE BUNGALOW-SUKHIAPOKHRI, DISTRICT : DARJEELING | SM/11953 | New | Material Requisition To Resource Division |  |  | RTOR000120/2022-2023 | 1897/NKWSMD | 15/12/2022 | 15/12/2022 | Resource Division | 3.25 | 0 | 0 | 0
2 | DARJEELING | Jorebunglow Sukiapokhri | Neorakhola W/S & Mtc.Div. | GRAVITY BASED WATER SUPPLY SCHEME FOR TAMSANG TEA GARDEN PWSS, BLOCK : JORE BUNGALOW-SUKHIAPOKHRI, DISTRICT : DARJEELING | SM/11953 | New | Material Requisition To Resource Division |  |  | RTOR000179/2022-2023 | 2578/NKWSMD | 17/02/2023 | 17/02/2023 | Resource Division | 3.25 | 0 | 0 | 0
3 | DARJEELING | Jorebunglow Sukiapokhri | Neorakhola W/S & Mtc.Div. | GRAVITY BASED WATER SUPPLY SCHEME FOR TAMSANG TEA GARDEN PWSS, BLOCK : JORE BUNGALOW-SUKHIAPOKHRI, DISTRICT : DARJEELING | SM/11953 | New | Continuation Engagement of 02 (Two) numbers Computer Operator (Graduate with Certificate in Computer Application) for the works related to Jal Jeevan Mission /Jal Swapno at the Office of the Executive Engineer, Neorakhola Water Supply & Maintenance Division, Public Health Engineering Directorate, Kalimpong from 01.06.2024 to 31.07.2024. | Assistant Engineer II | Junior Engineer I | ORD/000052/2024-2025 | 386/NKWSMD | 31/05/2024 | 31/07/2024 | YAMA CONSTRUCTIONS LLP | 0.79 | 0.79 | 100 | 100
4 | DARJEELING | Jorebunglow Sukiapokhri | Neorakhola W/S & Mtc.Div. | GRAVITY BASED WATER SUPPLY SCHEME FOR TAMSANG TEA GARDEN PWSS, BLOCK : JORE BUNGALOW-SUKHIAPOKHRI, DISTRICT : DARJEELING | SM/11953 | New | ADDITIONAL WORK FOR GRAVITY BASED WATER SUPPLY SCEME FOR TAMSANG TEA GARDEN PIPED WATER SUPPLY SCHEME, BLOCK-JOREBUNGLOW SUKIAPOKRI DISTRICT-DARJEELING (TSM/011759). |  |  | ORD/000043/2025-2026 | 648/NKWSMD | 05/05/2025 | 04/07/2025 | DAJUBHAI HARDWARE | 23.02 | 0 | 0 | 0
5 | DARJEELING | Jorebunglow Sukiapokhri | Neorakhola W/S & Mtc.Div. | GRAVITY BASED WATER SUPPLY SCHEME FOR TAMSANG TEA GARDEN PWSS, BLOCK : JORE BUNGALOW-SUKHIAPOKHRI, DISTRICT : DARJEELING | SM/11953 | New | Water Supply Scheme for Tamsang Tea Garden PWSS In Jore Bunglow Sukhiapokhari Under Darjeeling District. |  |  | ORD/000264/2022-2023 | 1562/NKWSMD | 21/10/2022 | 12/02/2025 | VINAYAK CONSTRUCTION | 736.38 | 691.04 | 93.84 | 100
Total | [13 empty] | 766.68 | 691.83 | 90.24