## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | DARJEELING | Jorebunglow Sukiapokhri | Neorakhola W/S & Mtc.Div. | GRAVITY BASED WATER SUPPLY SCHEME FOR MARIABONG PWSS, BLOCK : JORE BUNGALOW-SUKHIAPOKHRI - I, DISTRICT : DARJEELING | SM/12128 | New | Material Requisition To Resource Division |  |  | RTOR000114/2022-2023 | 1891/NKWSMD | 15/12/2022 |  | Resource Division | 4.68 | 0 | 0 | 0
2 | DARJEELING | Jorebunglow Sukiapokhri | Neorakhola W/S & Mtc.Div. | GRAVITY BASED WATER SUPPLY SCHEME FOR MARIABONG PWSS, BLOCK : JORE BUNGALOW-SUKHIAPOKHRI - I, DISTRICT : DARJEELING | SM/12128 | New | Material Requisition To Resource Division |  |  | RTOR000173/2022-2023 | 2609/NKWSMD | 17/02/2023 |  | Resource Division | 4.68 | 0 | 0 | 0
3 | DARJEELING | Jorebunglow Sukiapokhri | Neorakhola W/S & Mtc.Div. | GRAVITY BASED WATER SUPPLY SCHEME FOR MARIABONG PWSS, BLOCK : JORE BUNGALOW-SUKHIAPOKHRI - I, DISTRICT : DARJEELING | SM/12128 | New | permission fro laying 80mm dia GI Pipeline along the hill side of Darjeeling Ghoom Bhanjang Bijanbari Road |  |  | BILL/00206/2022-2023 | BP-2022-23-426 | 30/03/2023 |  | NEORAKHOLA W/S & MTC. DIV. | 10.35 | 0 | 0 | 0
4 | DARJEELING | Jorebunglow Sukiapokhri | Neorakhola W/S & Mtc.Div. | GRAVITY BASED WATER SUPPLY SCHEME FOR MARIABONG PWSS, BLOCK : JORE BUNGALOW-SUKHIAPOKHRI - I, DISTRICT : DARJEELING | SM/12128 | New | Proposed Gravity Based Water Supply Scheme for Mariabong Tea Garden PWSS In Jore Bunglow Sukhiapokhari Under Darjeeling District. |  |  | ORD/000236/2022-2023 | 1451/NKWSMD | 29/09/2022 | 26/07/2023 | GARGO TRADERS | 973.62 | 749.86 | 77.02 | 0
Total | [13 empty] | 993.32 | 749.86 | 75.49