## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | DARJEELING | Jorebunglow Sukiapokhri | Neorakhola W/S & Mtc.Div. | GRAVITY BASED WATER SUPPLY SCHEME FOR TUMSUNG KHASMAHAL PWSS BLOCK : JORE BUNGALOW-SUKHIAPOKHRI , DISTRICT : DARJEELING | SM/12178 | New | Proposed Gravity Based Water Supply Scheme for Tumsung Khasmahal PWSS In Jore Bunglow Sukhiapokhari Under Darjeeling District. |  |  | ORD/000240/2022-2023 | 1494/NKWSMD | 14/10/2022 | 10/07/2025 | ALLIED INSTRUMENTS | 587.51 | 574.91 | 97.86 | 100
2 | DARJEELING | Jorebunglow Sukiapokhri | Neorakhola W/S & Mtc.Div. | GRAVITY BASED WATER SUPPLY SCHEME FOR TUMSUNG KHASMAHAL PWSS BLOCK : JORE BUNGALOW-SUKHIAPOKHRI , DISTRICT : DARJEELING | SM/12178 | New | Material Requisition To Resource Division |  |  | RTOR000110/2022-2023 | 1887/NKWSMD | 15/12/2022 | 15/12/2022 | Resource Division | 1.74 | 0 | 0 | 0
3 | DARJEELING | Jorebunglow Sukiapokhri | Neorakhola W/S & Mtc.Div. | GRAVITY BASED WATER SUPPLY SCHEME FOR TUMSUNG KHASMAHAL PWSS BLOCK : JORE BUNGALOW-SUKHIAPOKHRI , DISTRICT : DARJEELING | SM/12178 | New | Material Requisition To Resource Division |  |  | RTOR000169/2022-2023 | 2606/NKWSMD | 17/02/2023 | 17/02/2023 | Resource Division | 1.74 | 0 | 0 | 0
Total | [13 empty] | 590.98 | 574.91 | 97.28