## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | DARJEELING | Jorebunglow Sukiapokhri | Neorakhola W/S & Mtc.Div. | GRAVITY BASED WATER SUPPLY SCHEME FOR LINGIA TEA GARDEN PWSS, BLOCK : JORE BUNGALOW-SUKHIAPOKHRI, DISTRICT : DARJEELING | SM/12179 | New | Material Requisition To Resource Division |  |  | RTOR000193/2022-2023 | 2581/NKWSMD | 17/02/2023 | 17/02/2023 | Resource Division | 2.75 | 0 | 0 | 0
2 | DARJEELING | Jorebunglow Sukiapokhri | Neorakhola W/S & Mtc.Div. | GRAVITY BASED WATER SUPPLY SCHEME FOR LINGIA TEA GARDEN PWSS, BLOCK : JORE BUNGALOW-SUKHIAPOKHRI, DISTRICT : DARJEELING | SM/12179 | New | ADDITIONAL WORK FOR GRAVITY BASED WATER SUPPLY SCHEME FOR LINGIA TEA GARDEN PIPED WATER SUPPLY SCHEME, BLOCK: JORE BUNGALOW SUKHIAPOKHRI, DISTRICT: DARJEELING UNDER DARJEELING DIVISION, P.H.E-GTA. |  |  | ORD/000042/2025-2026 | 647/NKWSMD | 05/05/2025 | 04/07/2025 | DAJUBHAI HARDWARE | 22.9 | 0 | 0 | 0
3 | DARJEELING | Jorebunglow Sukiapokhri | Neorakhola W/S & Mtc.Div. | GRAVITY BASED WATER SUPPLY SCHEME FOR LINGIA TEA GARDEN PWSS, BLOCK : JORE BUNGALOW-SUKHIAPOKHRI, DISTRICT : DARJEELING | SM/12179 | New | WATER SUPPLY SCHEME FOR LINGIA TEA GARDEN PWSS, BLOCK : JORE BUNGALOW-SUKHIAPOKHRI, DISTRICT : DARJEELING |  |  | ORD/000259/2022-2023 | 1622/NKWSMD | 03/11/2022 | 26/01/2025 | VINAYAK CONSTRUCTION | 633.65 | 0 | 0 | 100
Total | [13 empty] | 659.3 | 0 | 0