## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | DARJEELING | Darjeeling Pulbazar | Neorakhola W/S & Mtc.Div. | Choongtoong & Lizahill Tea Garden water supply scheme | SM/12269 | New | Material Requisition To Resource Division |  |  | RTOR000108/2022-2023 | 1885/NKWSMD | 15/12/2022 |  | Resource Division | 16.58 | 0 | 0 | 0
2 | DARJEELING | Darjeeling Pulbazar | Neorakhola W/S & Mtc.Div. | Choongtoong & Lizahill Tea Garden water supply scheme | SM/12269 | New | Material Requisition To Resource Division |  |  | RTOR000167/2022-2023 | 2604/NKWSMD | 17/02/2023 |  | Resource Division | 16.58 | 0 | 0 | 0
3 | DARJEELING | Darjeeling Pulbazar | Neorakhola W/S & Mtc.Div. | Choongtoong & Lizahill Tea Garden water supply scheme | SM/12269 | New | (CONTINUATION) ADDITIONAL ENGAGEMENT OF 01 (ONE) NUMBER COMPUTER OPERATOR (GRADUATE WITH CERTIFICATE IN COMPUTER APPLICATION) FOR THE WORKS RELATED TO JAL JEEVAN MISSION / JAL SWAPNO AT THE OFFICE OF THE SUPERINTENDING ENGINEER, GTA-CIRCLE, PUBLIC HEALTH ENGINEERING DIRECTORATE FROM 01.09.2023 TO 31.12.2023 |  |  | ORD/000220/2023-2024 | 1023/NKWSMD | 31/08/2023 | 29/12/2023 | QRT SECURITY AND MANPOWER SERVICE | 0.79 | 0 | 0 | 100
4 | DARJEELING | Darjeeling Pulbazar | Neorakhola W/S & Mtc.Div. | Choongtoong & Lizahill Tea Garden water supply scheme | SM/12269 | New | CHOONGTOONG & LIZAHILL TEA GARDEN WATER SUPPLY SCHEME UNDER DARJEELING DIVISION I, PHED, GTA |  |  | ORD/000239/2022-2023 | 1447/NKWSMD | 29/09/2022 | 26/07/2023 | SUDESH RAYA MAJHI | 1203.75 | 763.89 | 63.46 | 90
Total | [13 empty] | 1237.7 | 763.89 | 61.72