## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | DARJEELING | Kurseong | Neorakhola W/S & Mtc.Div. | PWS Scheme for Rolak Khasmahal & Lonku Khasmahal under Kurseong Sub - Division, PHED, GTA. | SM/12366 | New | Material Requisition To Resource Division |  |  | RTOR000208/2022-2023 | 2556/NKWSMD | 17/02/2023 | 17/02/2023 | Resource Division | 8.37 | 0 | 0 | 0
2 | DARJEELING | Kurseong | Neorakhola W/S & Mtc.Div. | PWS Scheme for Rolak Khasmahal & Lonku Khasmahal under Kurseong Sub - Division, PHED, GTA. | SM/12366 | New | Material Requisition To Resource Division |  |  | RTOR000151/2022-2023 | 2071/NKWSMD | 05/01/2023 | 05/01/2023 | Resource Division | 8.37 | 0 | 0 | 0
3 | DARJEELING | Kurseong | Neorakhola W/S & Mtc.Div. | PWS Scheme for Rolak Khasmahal & Lonku Khasmahal under Kurseong Sub - Division, PHED, GTA. | SM/12366 | New | Material Requisition To Resource Division |  |  | RTOR000238/2022-2023 | 2723/NKWSMD | 03/03/2023 | 03/03/2023 | Resource Division | 8.37 | 0 | 0 | 0
4 | DARJEELING | Kurseong | Neorakhola W/S & Mtc.Div. | PWS Scheme for Rolak Khasmahal & Lonku Khasmahal under Kurseong Sub - Division, PHED, GTA. | SM/12366 | New | ADDITIONAL WORK FOR PIPED WATER SUPPLY SCHEME FOR ROLAK KHASMAHAL & LONKU KHASMAHAL UNDER KURSEONG BLOCK DISTRICT-DARJEELING UNDER KURSEONG DIVISION. |  |  | ORD/000041/2025-2026 | 656/NKWSMD | 05/05/2025 | 01/11/2025 | DAJUBHAI CONSTRUCTION | 83.76 | 0 | 0 | 0
5 | DARJEELING | Kurseong | Neorakhola W/S & Mtc.Div. | PWS Scheme for Rolak Khasmahal & Lonku Khasmahal under Kurseong Sub - Division, PHED, GTA. | SM/12366 | New | Surface water based Rolak Khasmahal & Lonku Khasmahal Piped Water Supply Scheme to accommodate FHTC in Kurseong Block within Darjeeling District. |  |  | ORD/000314/2022-2023 | 2494/NKWSMD | 09/02/2023 | 15/12/2026 | VINAYAK CONSTRUCTION | 1016.14 | 0 | 0 | 100
Total | [13 empty] | 1125 | 0 | 0