## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | DARJEELING | Kurseong | Neorakhola W/S & Mtc.Div. | PWS Scheme for Longview Tea Garden under Kurseong Sub - Division, PHED, GTA. | SM/12367 | New | Material Requisition To Resource Division |  |  | RTOR000213/2022-2023 | 2561/NKWSMD | 17/02/2023 | 17/02/2023 | Resource Division | 8.11 | 0 | 0 | 0
2 | DARJEELING | Kurseong | Neorakhola W/S & Mtc.Div. | PWS Scheme for Longview Tea Garden under Kurseong Sub - Division, PHED, GTA. | SM/12367 | New | SURFACE WATER BASED LONGVIEW PWSS TO ACCOMODTE FHTC IN KURSOENG BLOCK WITHIN DARJEELING DISTRICT UNDER KURSEONG DIVISION, PHE DTE |  |  | ORD/000307/2022-2023 | 2471/NKWSMD | 06/02/2023 | 06/05/2024 | SHAKTI CONSTRUCTION | 1742.62 | 1500.42 | 86.1 | 100
Total | [13 empty] | 1750.73 | 1500.42 | 85.7