## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | DARJEELING | Kurseong | Neorakhola W/S & Mtc.Div. | PWS Scheme for Barasit Tong Khasmahal & Selphu Khasmahal under Kurseong Sub - Division, PHED, GTA. | SM/12368 | New | Material Requisition To Resource Division |  |  | RTOR000198/2022-2023 | 2594/NKWSMD | 17/02/2023 | 17/02/2023 | Resource Division | 5.35 | 0 | 0 | 0
2 | DARJEELING | Kurseong | Neorakhola W/S & Mtc.Div. | PWS Scheme for Barasit Tong Khasmahal & Selphu Khasmahal under Kurseong Sub - Division, PHED, GTA. | SM/12368 | New | Material Requisition To Resource Division |  |  | RTOR000150/2022-2023 | 2070/NKWSMD | 05/01/2023 | 05/01/2023 | Resource Division | 10.71 | 0 | 0 | 0
3 | DARJEELING | Kurseong | Neorakhola W/S & Mtc.Div. | PWS Scheme for Barasit Tong Khasmahal & Selphu Khasmahal under Kurseong Sub - Division, PHED, GTA. | SM/12368 | New | FOREST PAYMENT |  |  | BILL/00760/2023-2024 |  | 15/02/2024 | 15/02/2024 | DIVISIONAL FOREST OFFICER | 10.71 | 0 | 0 | 0
4 | DARJEELING | Kurseong | Neorakhola W/S & Mtc.Div. | PWS Scheme for Barasit Tong Khasmahal & Selphu Khasmahal under Kurseong Sub - Division, PHED, GTA. | SM/12368 | New | forest payment |  |  | BILL/01003/2023-2024 | BP-2023-24-601 | 18/03/2024 | 18/03/2024 | DIVISIONAL FOREST OFFICER | 3.28 | 0 | 0 | 0
5 | DARJEELING | Kurseong | Neorakhola W/S & Mtc.Div. | PWS Scheme for Barasit Tong Khasmahal & Selphu Khasmahal under Kurseong Sub - Division, PHED, GTA. | SM/12368 | New | Surface water based Barasitting Khasmahal & Selpu Khasmahal PWSS to accommodate FHTC in Kurseong Block within Darjeeling District |  |  | ORD/000305/2022-2023 | 2362/NKWSMD | 01/02/2023 | 08/09/2024 | YAMA CONSTRUCTIONS LLP | 1751.75 | 0 | 0 | 100
6 | DARJEELING | Kurseong | Neorakhola W/S & Mtc.Div. | PWS Scheme for Barasit Tong Khasmahal & Selphu Khasmahal under Kurseong Sub - Division, PHED, GTA. | SM/12368 | New | ADDITIONAL WORK FOR SURFACE WATER BASED BARASITTONG KHASMAHAL & SELPU KHASMAHAL PIPED WATER SUPPLY SCHEME TO ACCOMMODATE FHTC IN KURSEONG BLOCK WITHIN DARJEELING DISTRICT. |  |  | ORD/000128/2024-2025 | 2205/NKWSMD | 02/12/2024 | 31/05/2025 | YAMA CONSTRUCTIONS LLP | 246.9 | 0 | 0 | 80
Total | [13 empty] | 2028.71 | 0 | 0