## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | DARJEELING | Jorebunglow Sukiapokhri | Neorakhola W/S & Mtc.Div. | GRAVITY BASED WATER SUPPLY SCHEME FOR SONADA FOREST PWSS IN JORE BUNGLOW SUKHIA POKHARI BLOCK UNDER DARJEELING DISTRICT. | SM/12983 | New | WATER SUPPLY SCHEME FOR SONADA FOREST PWSS IN JOREBUNGLOW SUKIAPOKHARI BLOCK UNDER DARJEELING DISTRICT. |  |  | ORD/000308/2022-2023 | 2472/NKWSMD | 06/02/2023 | 07/11/2025 | M/S. ASHOK KUMAR PERIWAL | 1198.11 | 572.16 | 47.76 | 85
2 | DARJEELING | Jorebunglow Sukiapokhri | Neorakhola W/S & Mtc.Div. | GRAVITY BASED WATER SUPPLY SCHEME FOR SONADA FOREST PWSS IN JORE BUNGLOW SUKHIA POKHARI BLOCK UNDER DARJEELING DISTRICT. | SM/12983 | New | Continuation Engagement of 1 (One) number Computer Operator (Graduate with Certificate in Computer Application) for the works related to Jal Jeevan Mission/ Jal Swapno at the Office of the Executive Engineer, Neorakhola Water Supply and Maintenance Division, Public Health Engineering Directorate from 01/12/2023 to 31/01/2024 | Assistant Engineer II | Junior Engineer I | ORD/000252/2023-2024 | 1469/NKWSMD | 01/12/2023 | 01/02/2024 | THE ELECTRIC SPHERE | 0.41 | 0 | 0 | 0
3 | DARJEELING | Jorebunglow Sukiapokhri | Neorakhola W/S & Mtc.Div. | GRAVITY BASED WATER SUPPLY SCHEME FOR SONADA FOREST PWSS IN JORE BUNGLOW SUKHIA POKHARI BLOCK UNDER DARJEELING DISTRICT. | SM/12983 | New | Material Requisition To Resource Division |  |  | RTOR000203/2022-2023 | 2595/NKWSMD | 17/02/2023 | 17/02/2023 | Resource Division | 8.26 | 0 | 0 | 0
4 | DARJEELING | Jorebunglow Sukiapokhri | Neorakhola W/S & Mtc.Div. | GRAVITY BASED WATER SUPPLY SCHEME FOR SONADA FOREST PWSS IN JORE BUNGLOW SUKHIA POKHARI BLOCK UNDER DARJEELING DISTRICT. | SM/12983 | New | Material Requisition To Resource Division |  |  | RTOR000061/2023-2024 | 571/NKWSMD | 22/06/2023 | 22/06/2023 | Resource Division | 7.02 | 0 | 0 | 0
5 | DARJEELING | Jorebunglow Sukiapokhri | Neorakhola W/S & Mtc.Div. | GRAVITY BASED WATER SUPPLY SCHEME FOR SONADA FOREST PWSS IN JORE BUNGLOW SUKHIA POKHARI BLOCK UNDER DARJEELING DISTRICT. | SM/12983 | New | (CONTINUATION) ADDITIONAL ENGAGEMENT OF 01 (ONE) NUMBER COMPUTER OPERATOR (GRADUATE WITH CERTIFICATE IN COMPUTER APPLICATION) FOR THE WORKS RELATED TO JAL JEEVAN MISSION / JAL SWAPNO AT THE OFFICE OF THE SUPERINTENDING ENGINEER, GTA-CIRCLE, PUBLIC HEALTH ENGINEERING DIRECTORATE FROM 01.05.2024 TO 31.08.2024. | Assistant Engineer II | Junior Engineer I | ORD/000001/2024-2025 | 779/NKWSMD | 30/04/2024 | 31/08/2024 | QRT SECURITY AND MANPOWER SERVICE | 0.79 | 0.39 | 50 | 100
6 | DARJEELING | Jorebunglow Sukiapokhri | Neorakhola W/S & Mtc.Div. | GRAVITY BASED WATER SUPPLY SCHEME FOR SONADA FOREST PWSS IN JORE BUNGLOW SUKHIA POKHARI BLOCK UNDER DARJEELING DISTRICT. | SM/12983 | New | GRAVITY BASED WATER SUPPLY SCHEME FOR SONADA FOREST UNDER KURSEONG DIVISION. SCHEME CODE - 12983 TSM/012820 |  |  | BILL/00089/2024-2025 | BP-2024-25-96 | 08/07/2024 | 08/07/2024 | DIVISIONAL FOREST OFFICER | 8.41 | 0 | 0 | 0
Total | [13 empty] | 1222.98 | 572.55 | 46.82