## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | DARJEELING | Jorebunglow Sukiapokhri | Neorakhola W/S & Mtc.Div. | GRAVITY BASED WATER SUPPLY SCHEME FOR PARAMAGURI KHASMAHAL PWSS, BLOCK : JORE BUNGALOW-SUKHIAPOKHRI , DISTRICT : DARJEELING | SM/13042 | New | Material Requisition To Resource Division |  |  | RTOR000117/2022-2023 | 1894/NKWSMD | 15/12/2022 | 15/12/2022 | Resource Division | 3.56 | 0 | 0 | 0
2 | DARJEELING | Jorebunglow Sukiapokhri | Neorakhola W/S & Mtc.Div. | GRAVITY BASED WATER SUPPLY SCHEME FOR PARAMAGURI KHASMAHAL PWSS, BLOCK : JORE BUNGALOW-SUKHIAPOKHRI , DISTRICT : DARJEELING | SM/13042 | New | Material Requisition To Resource Division |  |  | RTOR000176/2022-2023 | 2608/NKWSMD | 17/02/2023 | 17/02/2023 | Resource Division | 3.56 | 0 | 0 | 0
3 | DARJEELING | Jorebunglow Sukiapokhri | Neorakhola W/S & Mtc.Div. | GRAVITY BASED WATER SUPPLY SCHEME FOR PARAMAGURI KHASMAHAL PWSS, BLOCK : JORE BUNGALOW-SUKHIAPOKHRI , DISTRICT : DARJEELING | SM/13042 | New | WATER SUPPLY SCHEME FOR PARMAGURI KHASMAHAL PWSS IN BLOCK JOREBUNGLOW SUKIAPOKRI UNDER DISTRICT DARJEELING. |  |  | ORD/000238/2022-2023 | 1454/NKWSMD | 29/09/2022 | 26/07/2023 | MADAN SHARMA | 1011.5 | 955.04 | 94.42 | 99
4 | DARJEELING | Jorebunglow Sukiapokhri | Neorakhola W/S & Mtc.Div. | GRAVITY BASED WATER SUPPLY SCHEME FOR PARAMAGURI KHASMAHAL PWSS, BLOCK : JORE BUNGALOW-SUKHIAPOKHRI , DISTRICT : DARJEELING | SM/13042 | New | (Continuation) Engagement of 01 (One) number Computer Operator (Graduate with Certificate in Computer Application) for the works related to Jal Jeevan Mission /Jal Swapno at the Office of the Executive Engineer, Neorakhola Water Supply & Maintenance Division, Public Health Engineering Directorate, Kalimpong from 01.08.2024 to 31.08.2024 | Assistant Engineer II | Junior Engineer I | ORD/000097/2024-2025 | 1347/NKWSMD | 31/07/2024 | 31/08/2024 | YAMA CONSTRUCTIONS LLP | 0.2 | 0 | 0 | 100
Total | [13 empty] | 1018.82 | 955.04 | 93.74