## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | DARJEELING | Jorebunglow Sukiapokhri | Neorakhola W/S & Mtc.Div. | DETAILED PROJECT REPORT FOR WATER SUPPLY SCHEME FOR MOONDA KOTEE TEA GARDEN PWSS, BLOCK: JORE BUNGALOW-SUKHIAPOKHRI, DISTRICT: DARJEELING. | SM/13571 | New | WATER SUPPLY SCHEME FOR MOONDA KOTTE TEA GARDEN PIPED WATER SUPPLY SCHEME IN BLOCK JOREBUNGLOW SUKIAPOKRI UNDER DISTRICT DARJEELING. |  |  | ORD/000337/2022-2023 | 2734/NKWSMD | 03/03/2023 | 29/08/2024 | SRINIWAS AGARWAL | 1366.07 | 1120.94 | 82.06 | 70
2 | DARJEELING | Jorebunglow Sukiapokhri | Neorakhola W/S & Mtc.Div. | DETAILED PROJECT REPORT FOR WATER SUPPLY SCHEME FOR MOONDA KOTEE TEA GARDEN PWSS, BLOCK: JORE BUNGALOW-SUKHIAPOKHRI, DISTRICT: DARJEELING. | SM/13571 | New | Material Requisition To Resource Division |  |  | RTOR000253/2022-2023 | 2746/NKWSMD | 06/03/2023 | 06/03/2023 | Resource Division | 7.15 | 0 | 0 | 0
3 | DARJEELING | Jorebunglow Sukiapokhri | Neorakhola W/S & Mtc.Div. | DETAILED PROJECT REPORT FOR WATER SUPPLY SCHEME FOR MOONDA KOTEE TEA GARDEN PWSS, BLOCK: JORE BUNGALOW-SUKHIAPOKHRI, DISTRICT: DARJEELING. | SM/13571 | New | ADDITIONAL WORK FOR MOONDA KOTHI TEA GARDEN PIPED WATER SUPPLY SCHEME UNDER BLOCK-JOREBUNGLOW SUKIAPOKRI DISTRICT-DARJEELING UNDER KURSEONG DIVISION PHED GTA. |  |  | ORD/000033/2025-2026 | 635/NKWSMD | 05/05/2025 | 03/08/2025 | SRINIWAS AGARWAL | 38.65 | 0 | 0 | 0
Total | [13 empty] | 1411.87 | 1120.94 | 79.39