## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | DARJEELING | Kurseong | Neorakhola W/S & Mtc.Div. | MAHAL DIRAM TEA GARDEN PWSS | SM/13623 | New | WATER SUPPLY SCHEME FOR MAHAL DIRAM TEA GARDEN PIPED WATER SUPPLY SCHEME KURSEONG BLOCK UNDER DARJEELING DISTRICT. |  |  | ORD/000324/2022-2023 | 2655/NKWSMD | 28/02/2023 | 19/11/2024 | MS. SURYA I PVT. LTD COMPANY | 212.76 | 79.52 | 37.37 | 85
2 | DARJEELING | Kurseong | Neorakhola W/S & Mtc.Div. | MAHAL DIRAM TEA GARDEN PWSS | SM/13623 | New | Material Requisition To Resource Division |  |  | RTOR000245/2022-2023 | 2720/NKWSMD | 03/03/2023 | 03/03/2023 | Resource Division | 1.02 | 0 | 0 | 0
3 | DARJEELING | Kurseong | Neorakhola W/S & Mtc.Div. | MAHAL DIRAM TEA GARDEN PWSS | SM/13623 | New | Material Requisition To Resource Division |  |  | RTOR000133/2023-2024 | 263/NKWSMD | 20/02/2024 | 20/02/2024 | Resource Division | 2.17 | 0 | 0 | 0
4 | DARJEELING | Kurseong | Neorakhola W/S & Mtc.Div. | MAHAL DIRAM TEA GARDEN PWSS | SM/13623 | New | ADDITIONAL WORK FOR MAHALDIRAM TEA GARDEN PIPED WATER SUPPLY SCHEME UNDER BLOCK KURSEONG DISTRICT DARJEELING, KURSEONG DIVISION PHED. |  |  | ORD/000369/2025-2026 | 803/NKWSMD | 03/06/2025 | 02/08/2025 | YADI LEPCHA | 10.56 | 0 | 0 | 0
5 | DARJEELING | Kurseong | Neorakhola W/S & Mtc.Div. | MAHAL DIRAM TEA GARDEN PWSS | SM/13623 | New | water supply scheme for mahaldiram tea garden pwss in kurseong block |  |  | BILL/00678/2024-2025 | BP-2024-25-486 | 17/03/2025 | 17/03/2025 | DIVISIONAL FOREST OFFICER | 3.38 | 0 | 0 | 0
Total | [13 empty] | 229.9 | 79.52 | 34.59