## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | DARJEELING | Jorebunglow Sukiapokhri | Neorakhola W/S & Mtc.Div. | GRAVITY BASED WATER SUPPLY SCHEME FOR SENCHAL FOREST PWSS IN JORE BUNGLOW SUKHIAPOKHRI BLOCK UNDER DARJEELING DISTRICT. | SM/13956 | New | Material Requisition To Resource Division |  |  | RTOR000006/2023-2024 | 153/NKWSMD | 03/05/2023 | 03/05/2023 | Resource Division | 2.42 | 0 | 0 | 0
2 | DARJEELING | Jorebunglow Sukiapokhri | Neorakhola W/S & Mtc.Div. | GRAVITY BASED WATER SUPPLY SCHEME FOR SENCHAL FOREST PWSS IN JORE BUNGLOW SUKHIAPOKHRI BLOCK UNDER DARJEELING DISTRICT. | SM/13956 | New | Gravity Base Water Supply Scheme for Senchal-I under Jal Jeevan Mission Detail - (SW No. : SW/145710/2023) |  |  | BILL/00389/2024-2025 | BP-2024-25-452 | 09/12/2024 | 09/12/2024 | DIVISIONAL FOREST OFFICER | 5.7 | 0 | 0 | 0
3 | DARJEELING | Jorebunglow Sukiapokhri | Neorakhola W/S & Mtc.Div. | GRAVITY BASED WATER SUPPLY SCHEME FOR SENCHAL FOREST PWSS IN JORE BUNGLOW SUKHIAPOKHRI BLOCK UNDER DARJEELING DISTRICT. | SM/13956 | New | Gravity Base Water Supply Scheme for Senchal III under Jal Jeevan Mission Detail - (SW No. : SW/145713/2023) WEST BENGAL , DARJEELING |  |  | BILL/00391/2024-2025 |  | 20/09/2024 | 20/09/2024 | DIVISIONAL FOREST OFFICER | 6.86 | 0 | 0 | 0
4 | DARJEELING | Jorebunglow Sukiapokhri | Neorakhola W/S & Mtc.Div. | GRAVITY BASED WATER SUPPLY SCHEME FOR SENCHAL FOREST PWSS IN JORE BUNGLOW SUKHIAPOKHRI BLOCK UNDER DARJEELING DISTRICT. | SM/13956 | New | Gravity Based water supply scheme for Senchal-2 under JAl JEEWAN MISSION. Detail - (SW No. : SW/145709/2023) |  |  | BILL/00390/2024-2025 |  | 20/09/2024 | 20/09/2024 | DIVISIONAL FOREST OFFICER | 6.24 | 0 | 0 | 0
5 | DARJEELING | Jorebunglow Sukiapokhri | Neorakhola W/S & Mtc.Div. | GRAVITY BASED WATER SUPPLY SCHEME FOR SENCHAL FOREST PWSS IN JORE BUNGLOW SUKHIAPOKHRI BLOCK UNDER DARJEELING DISTRICT. | SM/13956 | New | Gravity Base Water Supply Scheme for Senchal III under Jal Jeevan Mission |  |  | BILL/00645/2024-2025 | BP-2024-25-454 | 09/12/2024 | 09/12/2024 | DIVISIONAL FOREST OFFICER | 6.86 | 0 | 0 | 0
6 | DARJEELING | Jorebunglow Sukiapokhri | Neorakhola W/S & Mtc.Div. | GRAVITY BASED WATER SUPPLY SCHEME FOR SENCHAL FOREST PWSS IN JORE BUNGLOW SUKHIAPOKHRI BLOCK UNDER DARJEELING DISTRICT. | SM/13956 | New | Gravity based water supply scheme for Senchal - 2 under JAL JEEWAN MISSION DETAILS (SW/145709/2023) |  |  | BILL/00646/2024-2025 | BP-2024-25-456 | 09/12/2024 | 09/12/2024 | DIVISIONAL FOREST OFFICER | 6.24 | 0 | 0 | 0
7 | DARJEELING | Jorebunglow Sukiapokhri | Neorakhola W/S & Mtc.Div. | GRAVITY BASED WATER SUPPLY SCHEME FOR SENCHAL FOREST PWSS IN JORE BUNGLOW SUKHIAPOKHRI BLOCK UNDER DARJEELING DISTRICT. | SM/13956 | New | DETAILED PROJECT REPORT FOR GRAVITY BASED WATER SUPPLY SCHEME FOR SENCHAL FOREST PIPED WATER SUPPLY SCHEME IN JOREBUNGLOW SUKIAPOKHARI BLOCK UNDER DARJEELING DISTRICT. |  |  | ORD/000018/2023-2024 | 118/NKWSMD | 28/04/2023 | 27/12/2025 | SUMAN THAKURI | 483 | 0 | 0 | 70
Total | [13 empty] | 517.33 | 0 | 0