## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | DARJEELING | Kurseong | Neorakhola W/S & Mtc.Div. | DETAILED PROJECT REPORT FOR WATER SUPPLY SCHEME FOR KARBIA TEA GARDEN PWSS IN KURSEONG BLOCK UNDER DARJEELING DISTRICT. | SM/13957 | New | Material Requisition To Resource Division |  |  | RTOR000202/2022-2023 | 2551/NKWSMD | 17/02/2023 | 17/02/2023 | Resource Division | 1.08 | 0 | 0 | 0
2 | DARJEELING | Kurseong | Neorakhola W/S & Mtc.Div. | DETAILED PROJECT REPORT FOR WATER SUPPLY SCHEME FOR KARBIA TEA GARDEN PWSS IN KURSEONG BLOCK UNDER DARJEELING DISTRICT. | SM/13957 | New | WATER SUPPLY SCHEME FOR KARBIA TEA GARDEN PIPED WATER SUPPLY SCHEME IN KURSEONG BLOCK UNDER DARJEELING DISTRICT. |  |  | ORD/000291/2022-2023 | 2148/NKWSMD | 20/01/2023 | 17/09/2023 | M/S. ASHOK KUMAR PERIWAL | 390.86 | 0 | 0 | 50
Total | [13 empty] | 391.94 | 0 | 0