## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | DARJEELING | Mirik | Neorakhola W/S & Mtc.Div. | WATER SUPPLY SCHEME FOR MANJUA FOREST PWSS IN MIRIK BLOCK UNDER DARJEELING DISTRICT. | SM/14147 | New | WATER SUPPLY SCHEME FOR MANJUA FOREST SOURENI -II PIPED WATER SUPPLY SCHEME IN MIRIK BLOCK UNDER DARJEELING DISTRICT. |  |  | ORD/000035/2023-2024 | 109/NKWSMD | 28/04/2023 | 22/01/2025 | MAA MANASA VYAPAAR | 1093.84 | 725.36 | 66.31 | 50
2 | DARJEELING | Mirik | Neorakhola W/S & Mtc.Div. | WATER SUPPLY SCHEME FOR MANJUA FOREST PWSS IN MIRIK BLOCK UNDER DARJEELING DISTRICT. | SM/14147 | New | Material Requisition To Resource Division |  |  | RTOR000028/2023-2024 | 245/NKWSMD | 12/05/2023 | 12/05/2023 | Resource Division | 5.91 | 0 | 0 | 0
3 | DARJEELING | Mirik | Neorakhola W/S & Mtc.Div. | WATER SUPPLY SCHEME FOR MANJUA FOREST PWSS IN MIRIK BLOCK UNDER DARJEELING DISTRICT. | SM/14147 | New | PAYMENT FOR WBSEDCL |  |  | BILL/00821/2023-2024 | BP-2023-24-530 | 26/02/2024 | 26/02/2024 | WBSEDCL | 6.32 | 0 | 0 | 0
4 | DARJEELING | Mirik | Neorakhola W/S & Mtc.Div. | WATER SUPPLY SCHEME FOR MANJUA FOREST PWSS IN MIRIK BLOCK UNDER DARJEELING DISTRICT. | SM/14147 | New | ADDITIONAL WORK FOR WATER SUPPLY SCHEME FOR MANJUA FOREST SOURINI-II PIPED WATER SUPPLY SCHEME IN MIRIK BLOCK UNDER DARJEELING DISTRICT. |  |  | ORD/000027/2025-2026 | 595/NKWSMD | 29/04/2025 | 28/06/2025 | ALLIED INSTRUMENTS | 13.7 | 0 | 0 | 0
Total | [13 empty] | 1119.78 | 725.36 | 64.78