## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | DARJEELING | Kurseong | Neorakhola W/S & Mtc.Div. | PROJECT REPORT FOR WATER SUPPLY SCHEME FOR GIDDA PAHAR PWSS IN KURSEONG BLOCK UNDER DARJEELING DISTRICT. | SM/14149 | New | WATER SUPPLY SCHEME FOR GIDDA PAHAR FOREST PIPED WATER SUPPLY SCHEME IN KURSEONG BLOCK UNDER DARJEELING DISTRICT. |  |  | ORD/000316/2022-2023 | 2520/NKWSMD | 15/02/2023 | 13/08/2026 | VINAYAK CONSTRUCTION | 1768.52 | 1015.99 | 57.45 | 85
2 | DARJEELING | Kurseong | Neorakhola W/S & Mtc.Div. | PROJECT REPORT FOR WATER SUPPLY SCHEME FOR GIDDA PAHAR PWSS IN KURSEONG BLOCK UNDER DARJEELING DISTRICT. | SM/14149 | New | Material Requisition To Resource Division |  |  | RTOR000210/2022-2023 | 2558/NKWSMD | 17/02/2023 | 17/02/2023 | Resource Division | 5.83 | 0 | 0 | 0
3 | DARJEELING | Kurseong | Neorakhola W/S & Mtc.Div. | PROJECT REPORT FOR WATER SUPPLY SCHEME FOR GIDDA PAHAR PWSS IN KURSEONG BLOCK UNDER DARJEELING DISTRICT. | SM/14149 | New | Material Requisition To Resource Division |  |  | RTOR000242/2022-2023 | 2715/NKWSMD | 03/03/2023 | 03/03/2023 | Resource Division | 5.83 | 0 | 0 | 0
4 | DARJEELING | Kurseong | Neorakhola W/S & Mtc.Div. | PROJECT REPORT FOR WATER SUPPLY SCHEME FOR GIDDA PAHAR PWSS IN KURSEONG BLOCK UNDER DARJEELING DISTRICT. | SM/14149 | New | forest clearance of JJM schemes under kurseong Division PHED GTA. |  |  | BILL/00448/2023-2024 | BP-2023-24-289 | 01/11/2023 | 01/11/2023 | DIVISIONAL FOREST OFFICER | 49.25 | 0 | 0 | 0
5 | DARJEELING | Kurseong | Neorakhola W/S & Mtc.Div. | PROJECT REPORT FOR WATER SUPPLY SCHEME FOR GIDDA PAHAR PWSS IN KURSEONG BLOCK UNDER DARJEELING DISTRICT. | SM/14149 | New | ADDITIONAL WORK FOR GIDDA PAHAR FOREST PIPED WATER SUPPLY SCHEME UNDER BLOCK KURSEONG DISTRICT-DARJEELING, KURSEONG DIVISION PHED-GTA. |  |  | ORD/000035/2025-2026 | 651/NKWSMD | 05/05/2025 | 01/11/2025 | MAGMA CONSORTIUM | 61.66 | 0 | 0 | 0
Total | [13 empty] | 1891.09 | 1015.99 | 53.72