## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | DARJEELING | Jorebunglow Sukiapokhri | Neorakhola W/S & Mtc.Div. | GRAVITY BASED WATER SUPPLY FOR PULUNGDONG KHASMAHAL PWSS | SM/14418 | New | Material Requisition To Resource Division |  |  | RTOR000211/2022-2023 | 2559/NKWSMD | 17/02/2023 | 17/02/2023 | Resource Division | 6.78 | 0 | 0 | 0
2 | DARJEELING | Jorebunglow Sukiapokhri | Neorakhola W/S & Mtc.Div. | GRAVITY BASED WATER SUPPLY FOR PULUNGDONG KHASMAHAL PWSS | SM/14418 | New | Material Requisition To Resource Division |  |  | RTOR000241/2022-2023 | 2717/NKWSMD | 03/03/2023 | 03/03/2023 | Resource Division | 6.78 | 0 | 0 | 0
3 | DARJEELING | Jorebunglow Sukiapokhri | Neorakhola W/S & Mtc.Div. | GRAVITY BASED WATER SUPPLY FOR PULUNGDONG KHASMAHAL PWSS | SM/14418 | New | WATER SUPPLY SCHEME FOR PLUNGDUNG KHASMAHAL PIPED WATER SUPPLY SCHEME IN BLOCK JOREBUNGLOW SUKIAPOKRI UNDER DISTRICT DARJEELING. |  |  | ORD/000317/2022-2023 | 2521/NKWSMD | 15/02/2023 | 13/08/2024 | GARGO TRADERS | 1596.98 | 0 | 0 | 85
4 | DARJEELING | Jorebunglow Sukiapokhri | Neorakhola W/S & Mtc.Div. | GRAVITY BASED WATER SUPPLY FOR PULUNGDONG KHASMAHAL PWSS | SM/14418 | New | PROPOSED PUMPING BASED PIPED WATER SUPPLY SCHEME FOR RAMBI BAZAR DIF UNDER TEESTA G.P, BLOCK : KALIMPONG - I, DISTRICT:KALIMPONG |  |  | ORD/000322/2022-2023 | 2652/NKWSMD | 28/02/2023 | 25/10/2024 | KAMAKHAYA CONSTRUCTION | 179.69 | 0 | 0 | 80
5 | DARJEELING | Jorebunglow Sukiapokhri | Neorakhola W/S & Mtc.Div. | GRAVITY BASED WATER SUPPLY FOR PULUNGDONG KHASMAHAL PWSS | SM/14418 | New | ADDITIONAL WORK FOR WATER SUPPLY SCHEME FOR PLUNGDUNG KHASMAHAL PIPED WATER SUPPLY SCHEME IN BLOCK JOREBUNGLOW SUKHIAPOKHRI UNDER DARJEELING DISTRICT. |  |  | ORD/000022/2025-2026 | 590/NKWSMD | 29/04/2025 | 28/07/2025 | M/S BRM DEVELOPERS | 35.22 | 0 | 0 | 0
Total | [13 empty] | 1825.44 | 0 | 0