## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | DARJEELING | Jorebunglow Sukiapokhri | Neorakhola W/S & Mtc.Div. | WATER SUPPLY SCHEME FOR GOPAL DHARA TEA GARDEN PWSS IN JORE BUNGLOW SUKHIAPOKHRI BLOCK UNDER DARJEELING DISTRICT. | SM/14528 | New | Material Requisition To Resource Division |  |  | RTOR000039/2023-2024 | 326/NKWSMD | 24/05/2023 | 24/05/2023 | Resource Division | 4.87 | 0 | 0 | 0
2 | DARJEELING | Jorebunglow Sukiapokhri | Neorakhola W/S & Mtc.Div. | WATER SUPPLY SCHEME FOR GOPAL DHARA TEA GARDEN PWSS IN JORE BUNGLOW SUKHIAPOKHRI BLOCK UNDER DARJEELING DISTRICT. | SM/14528 | New | PAYMENT FOR WBSEDCL |  |  | BILL/00758/2023-2024 | BP-2023-24-503 | 17/02/2024 | 17/02/2024 | WBSEDCL | 5.5 | 0 | 0 | 0
3 | DARJEELING | Jorebunglow Sukiapokhri | Neorakhola W/S & Mtc.Div. | WATER SUPPLY SCHEME FOR GOPAL DHARA TEA GARDEN PWSS IN JORE BUNGLOW SUKHIAPOKHRI BLOCK UNDER DARJEELING DISTRICT. | SM/14528 | New | WATER SUPPLY SCHEME FOR GOPALDHARA TEA GARDEN PIPED WATER SUPPLY SCHEME IN JOREBUNGLOW SUKIAPOKHRI BLOCK UNDER DARJEELING DISTRICT. |  |  | ORD/000040/2023-2024 | 223/NKWSMD | 10/05/2023 | 29/08/2025 | GREENPRO ENGINEERING | 1051.51 | 0 | 0 | 100
Total | [13 empty] | 1061.88 | 0 | 0