## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | DARJEELING | Mirik | Neorakhola W/S & Mtc.Div. | PIPED WATER SUPPLY SCHEME FOR BUKIM TEA GARDEN IN MIRIK BLOCK UNDER DARJEELING DISTRICT. | SM/14529 | New | Material Requisition To Resource Division |  |  | RTOR000065/2023-2024 | 770/NKWSMD | 19/07/2023 | 19/07/2023 | Resource Division | 10.27 | 0 | 0 | 0
2 | DARJEELING | Mirik | Neorakhola W/S & Mtc.Div. | PIPED WATER SUPPLY SCHEME FOR BUKIM TEA GARDEN IN MIRIK BLOCK UNDER DARJEELING DISTRICT. | SM/14529 | New | WATER SUPPLY SCHEME FOR BUKIM TEA GARDEN PIPED WATER SUPPLY SCHEME IN MIRIK BLOCK UNDER DARJEELING DISTRICT. |  |  | ORD/000074/2023-2024 | 675/NKWSMD | 12/07/2023 | 09/09/2024 | YAMA CONSTRUCTIONS LLP | 2035.87 | 0 | 0 | 75
3 | DARJEELING | Mirik | Neorakhola W/S & Mtc.Div. | PIPED WATER SUPPLY SCHEME FOR BUKIM TEA GARDEN IN MIRIK BLOCK UNDER DARJEELING DISTRICT. | SM/14529 | New | PAYMENT FOR WBSEDCL |  |  | BILL/00768/2023-2024 | BP-2023-24-506 | 17/02/2024 | 17/02/2024 | WBSEDCL | 10.62 | 0 | 0 | 0
4 | DARJEELING | Mirik | Neorakhola W/S & Mtc.Div. | PIPED WATER SUPPLY SCHEME FOR BUKIM TEA GARDEN IN MIRIK BLOCK UNDER DARJEELING DISTRICT. | SM/14529 | New | payment for WBSEDCL |  |  | BILL/00767/2023-2024 | BP-2023-24-505 | 17/02/2024 | 17/02/2024 | WBSEDCL | 4.8 | 0 | 0 | 0
5 | DARJEELING | Mirik | Neorakhola W/S & Mtc.Div. | PIPED WATER SUPPLY SCHEME FOR BUKIM TEA GARDEN IN MIRIK BLOCK UNDER DARJEELING DISTRICT. | SM/14529 | New | WATER SUPPLY SCHEME FOR BUKIM TEA GARDEN PIPED WATER SUPPLY SCHEME IN MIRIK BLOCK UNDER DARJEELING DISTRICT. |  |  | BILL/00194/2024-2025 | BP-2024-25-171 | 30/07/2024 | 30/07/2024 | WBSEDCL | 0.95 | 0 | 0 | 0
6 | DARJEELING | Mirik | Neorakhola W/S & Mtc.Div. | PIPED WATER SUPPLY SCHEME FOR BUKIM TEA GARDEN IN MIRIK BLOCK UNDER DARJEELING DISTRICT. | SM/14529 | New | PAYMENT FOR WBSEDCL |  |  | BILL/00769/2023-2024 | BP-2023-24-507 | 17/02/2024 | 17/02/2024 | WBSEDCL | 0.96 | 0 | 0 | 0
Total | [13 empty] | 2063.47 | 0 | 0