## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | DARJEELING | Kurseong | Neorakhola W/S & Mtc.Div. | WATER SUPPLY SCHEME FOR MAJUA TEA GARDEN PWSS IN KURSEONG BLOCK UNDER DARJEELING DISTRICT | SM/14532 | New | WATER SUPPLY SCHEME FOR MAJUA TEA GARDEN PIPED WATER SUPPLY SCHEME IN KURSEONG BLOCK UNDER DARJEELING DISTRICT. |  |  | ORD/000066/2023-2024 | 362/NKWSMD | 29/05/2023 | 22/02/2027 | YAMA CONSTRUCTIONS LLP | 1365.56 | 1035.82 | 75.85 | 90
2 | DARJEELING | Kurseong | Neorakhola W/S & Mtc.Div. | WATER SUPPLY SCHEME FOR MAJUA TEA GARDEN PWSS IN KURSEONG BLOCK UNDER DARJEELING DISTRICT | SM/14532 | New | Material Requisition To Resource Division |  |  | RTOR000059/2023-2024 | 532/NKWSMD | 13/06/2023 | 13/06/2023 | Resource Division | 6.53 | 0 | 0 | 0
3 | DARJEELING | Kurseong | Neorakhola W/S & Mtc.Div. | WATER SUPPLY SCHEME FOR MAJUA TEA GARDEN PWSS IN KURSEONG BLOCK UNDER DARJEELING DISTRICT | SM/14532 | New | forest clearance of JJM schemes under kurseong Division PHED GTA. |  |  | BILL/00448/2023-2024 | BP-2023-24-289 | 01/11/2023 | 01/11/2023 | DIVISIONAL FOREST OFFICER | 49.25 | 0 | 0 | 0
4 | DARJEELING | Kurseong | Neorakhola W/S & Mtc.Div. | WATER SUPPLY SCHEME FOR MAJUA TEA GARDEN PWSS IN KURSEONG BLOCK UNDER DARJEELING DISTRICT | SM/14532 | New | ADDITIONAL WORK FOR WATER SUPPLY SCHEME FOR MAJUA TEA GARDEN PIPED WATER SUPPLY SCHEME IN KURSEONG BLOCK UNDER DARJEELING DISTRICT. |  |  | ORD/000222/2024-2025 | 408/NKWSMD | 26/03/2025 | 24/06/2025 | NIM TSHERING LEPCHA | 35.96 | 0 | 0 | 0
Total | [13 empty] | 1457.3 | 1035.82 | 71.08