## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | DARJEELING | Jorebunglow Sukiapokhri | Neorakhola W/S & Mtc.Div. | GRAVITY BASED WATER SUPPLY SCHEME FOR SAGMARU TEA GARDEN PWSS | SM/15224 | New | Material Requisition To Resource Division |  |  | RTOR000077/2023-2024 | 765/NKWSMD | 19/07/2023 | 19/07/2023 | Resource Division | 5.61 | 0 | 0 | 0
2 | DARJEELING | Jorebunglow Sukiapokhri | Neorakhola W/S & Mtc.Div. | GRAVITY BASED WATER SUPPLY SCHEME FOR SAGMARU TEA GARDEN PWSS | SM/15224 | New | WATER SUPPLY SCHEME FOR SAGMARU TEA GARDEN PIPED WATER SUPPLY SCHEME IN BLOCK JOREBUNGLOW SUKHIAPOKHRI UNDER DARJEELING DISTRICT. |  |  | ORD/000086/2023-2024 | 685/NKWSMD | 12/07/2023 | 08/03/2025 | GARGO TRADERS | 2047.06 | 1169.99 | 57.15 | 50
Total | [13 empty] | 2052.67 | 1169.99 | 57