## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | DARJEELING | Kurseong | Neorakhola W/S & Mtc.Div. | SUKNA PRATHAM KHANDA PIPED WATER SUPPLY SCHEME | SM/15647 | New | PIPED WATER SUPPLY SCHEME FOR SUKNA PRATHAM KHANDA TO ACCOMMODATE FHTC UNDER KURSEONG DIVISION, PHE DTE, GTA, DARJEELING. |  |  | ORD/000377/2022-2023 | 2873/NKWSMD | 23/03/2023 | 15/02/2025 | RESILIENCE INFRASTRUCTURE PRIVATE LIMITED | 488.43 | 53.61 | 10.98 | 52
2 | DARJEELING | Kurseong | Kurseong Division | SUKNA PRATHAM KHANDA PIPED WATER SUPPLY SCHEME | SM/15647 | New | Work Order for proposals to frame and put up for Forest land clearance for land parcels through PARIVESH portal of MOEF GOI, Kurseong under Kurseong division, PHED,GTA | Assistant Engineer 6,Assistant Engineer4 | Junior Engineer 12 | ORD/000001/2023-2024 | 515/EE/KD/PHED | 22/11/2023 | 02/12/2023 | HILL GROUND CONSULTANCY | 0.96 | 0.96 | 100 | 100
3 | DARJEELING | Kurseong | Kurseong Division | SUKNA PRATHAM KHANDA PIPED WATER SUPPLY SCHEME | SM/15647 | New | Continuation( Extension of contract for Forest land clearance for land parcels through PARIVESH portal of MOEF GOI, Kurseong Under Kurseong Division, PHED,GTA | Assistant Engineer4 | Junior Engineer 12 | ORD/000003/2023-2024 | 561/EE/KD/PHE/DTE | 06/12/2023 | 13/12/2023 | HILL GROUND CONSULTANCY | 0.96 | 0 | 0 | 100
4 | DARJEELING | Kurseong | Kurseong Division | SUKNA PRATHAM KHANDA PIPED WATER SUPPLY SCHEME | SM/15647 | New | Continuation( Extension of contract for Forest land clearance for land parcels through PARIVESH portal of MOEF GOI, Kurseong Under Kurseong Division, PHED,GTA | Assistant Engineer4 | Junior Engineer 12 | ORD/000004/2023-2024 | 577/EE.KD/PHE/GTA | 18/12/2023 | 25/12/2023 | HILL GROUND CONSULTANCY | 0.96 | 0 | 0 | 100
5 | DARJEELING | Kurseong | Kurseong Division | SUKNA PRATHAM KHANDA PIPED WATER SUPPLY SCHEME | SM/15647 | New | Continuation( Extension of contract for Forest land clearance for land parcels through PARIVESH portal of MOEF GOI, Kurseong Under Kurseong Division, PHED,GTA | Assistant Engineer4 | Junior Engineer 12 | ORD/000002/2023-2024 | 535/EE/KD/PHE/GTA | 29/11/2023 | 06/12/2023 | HILL GROUND CONSULTANCY | 0.96 | 0 | 0 | 100
6 | DARJEELING | Kurseong | Neorakhola W/S & Mtc.Div. | SUKNA PRATHAM KHANDA PIPED WATER SUPPLY SCHEME | SM/15647 | New | Material Requisition To Resource Division |  |  | RTOR000269/2022-2023 | 2892/NKWSMD | 29/03/2023 | 29/03/2023 | Resource Division | 6.38 | 0 | 0 | 0
7 | DARJEELING | Kurseong | Kurseong Division | SUKNA PRATHAM KHANDA PIPED WATER SUPPLY SCHEME | SM/15647 | New | Continuation( Extension of contract for Forest land clearance for land parcels through PARIVESH portal of MOEF GOI, Kurseong Under Kurseong Division, PHED,GTA | Assistant Engineer4 | Junior Engineer 12 | ORD/000008/2023-2024 | 65/EE/KD/PHE/GTA | 19/02/2024 | 26/02/2024 | HILL GROUND CONSULTANCY | 0.96 | 0 | 0 | 100
8 | DARJEELING | Kurseong | Kurseong Division | SUKNA PRATHAM KHANDA PIPED WATER SUPPLY SCHEME | SM/15647 | New | Continuation( Extension of contract for Forest land clearance for land parcels through PARIVESH portal of MOEF GOI, Kurseong Under Kurseong Division, PHED,GTA | Assistant Engineer4 | Junior Engineer 12 | ORD/000005/2023-2024 | 27/EE/KD/PHE/GTA | 22/01/2024 | 29/01/2024 | HILL GROUND CONSULTANCY | 0.96 | 0 | 0 | 100
9 | DARJEELING | Kurseong | Kurseong Division | SUKNA PRATHAM KHANDA PIPED WATER SUPPLY SCHEME | SM/15647 | New | Continuation( Extension of contract for Forest land clearance for land parcels through PARIVESH portal of MOEF GOI, Kurseong Under Kurseong Division, PHED,GTA | Assistant Engineer4 | Junior Engineer 12 | ORD/000006/2023-2024 | 35/EE/KD/PHE/GTA | 29/01/2024 | 05/02/2024 | HILL GROUND CONSULTANCY | 0.96 | 0 | 0 | 100
10 | DARJEELING | Kurseong | Kurseong Division | SUKNA PRATHAM KHANDA PIPED WATER SUPPLY SCHEME | SM/15647 | New | Continuation( Extension of contract for Forest land clearance for land parcels through PARIVESH portal of MOEF GOI, Kurseong Under Kurseong Division, PHED,GTA | Assistant Engineer4 | Junior Engineer 12 | ORD/000007/2023-2024 | 57/EE/KD/GTA | 09/02/2024 | 16/02/2024 | HILL GROUND CONSULTANCY | 0.96 | 0 | 0 | 100
11 | DARJEELING | Kurseong | Neorakhola W/S & Mtc.Div. | SUKNA PRATHAM KHANDA PIPED WATER SUPPLY SCHEME | SM/15647 | New | PIPED WATER SUPPLY SCHEME FOR SUKNA PRATHAM KHANDA. SCHEME CODE - 15647 TSM/017747 |  |  | BILL/00091/2024-2025 | "BP-2024-25-100 | 08/07/2024 | 08/07/2024 | DIVISIONAL FOREST OFFICER | 13.99 | 0 | 0 | 0
Total | [13 empty] | 516.45 | 54.57 | 10.57