## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | DARJEELING | Kurseong | Neorakhola W/S & Mtc.Div. | SUKNA PRATHAM KHANDA PIPED WATER SUPPLY SCHEME | SM/15647 | New | Material Requisition To Resource Division |  |  | RTOR000269/2022-2023 | 2892/NKWSMD | 29/03/2023 |  | Resource Division | 6.38 | 0 | 0 | 0
2 | DARJEELING | Kurseong | Neorakhola W/S & Mtc.Div. | SUKNA PRATHAM KHANDA PIPED WATER SUPPLY SCHEME | SM/15647 | New | PIPED WATER SUPPLY SCHEME FOR SUKNA PRATHAM KHANDA. SCHEME CODE - 15647 TSM/017747 |  |  | BILL/00091/2024-2025 | "BP-2024-25-100 | 08/07/2024 |  | DIVISIONAL FOREST OFFICER | 13.99 | 0 | 0 | null
3 | DARJEELING | Kurseong | Neorakhola W/S & Mtc.Div. | SUKNA PRATHAM KHANDA PIPED WATER SUPPLY SCHEME | SM/15647 | New | PIPED WATER SUPPLY SCHEME FOR SUKNA PRATHAM KHANDA TO ACCOMMODATE FHTC UNDER KURSEONG DIVISION, PHE DTE, GTA, DARJEELING. |  |  | ORD/000377/2022-2023 | 2873/NKWSMD | 23/03/2023 | 18/11/2023 | RESILIENCE INFRASTRUCTURE PRIVATE LIMITED | 488.43 | 0 | 0 | 40
Total | [13 empty] | 508.81 | 0 | 0