## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | DARJEELING | Kurseong | Neorakhola W/S & Mtc.Div. | PWS Scheme for Sepoy Dhura Tea Garden | SM/15651 | New | Material Requisition To Resource Division |  |  | RTOR000250/2022-2023 | 2727/NKWSMD | 03/03/2023 | 03/03/2023 | Resource Division | 2.33 | 0 | 0 | 0
2 | DARJEELING | Kurseong | Neorakhola W/S & Mtc.Div. | PWS Scheme for Sepoy Dhura Tea Garden | SM/15651 | New | Material Requisition To Resource Division |  |  | RTOR000260/2022-2023 | 2778/NKWSMD | 10/03/2023 | 10/03/2023 | Resource Division | 2.33 | 0 | 0 | 0
3 | DARJEELING | Kurseong | Neorakhola W/S & Mtc.Div. | PWS Scheme for Sepoy Dhura Tea Garden | SM/15651 | New | SURFACE WATER BASED SEPOYDHURA (ST MARYS -I) PIPED WATER SUPPLY SCHEME TO ACCOMODATE FHTC IN KURSEONG BLOCK. |  |  | ORD/000332/2022-2023 | 2706/NKWSMD | 02/03/2023 | 31/03/2025 | SHAKTI CONSTRUCTION | 442.13 | 156.8 | 35.46 | 90
4 | DARJEELING | Kurseong | Neorakhola W/S & Mtc.Div. | PWS Scheme for Sepoy Dhura Tea Garden | SM/15651 | New | ADDITIONAL WORK FOR PIPED WATER SUPPLY SCHEME FOR SEPOY DHURA TEA GARDEN IN KURSEONG BLOCK WITHIN DARJEELING DISTRICT. |  |  | ORD/000032/2025-2026 | 633/NKWSMD | 05/05/2025 | 01/11/2025 | MS CHAMLING CONSTRUCTION | 66.89 | 0 | 0 | 0
Total | [13 empty] | 513.68 | 156.8 | 30.53