## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | DARJEELING | Mirik | Neorakhola W/S & Mtc.Div. | PATONG TEA GARDEN PIPED WATER SUPPLY SCHEME | SM/15655 | New | Material Requisition To Resource Division |  |  | RTOR000020/2023-2024 | 205/NKWSMD | 10/05/2023 | 10/05/2023 | Resource Division | 4.29 | 0 | 0 | 0
2 | DARJEELING | Mirik | Neorakhola W/S & Mtc.Div. | PATONG TEA GARDEN PIPED WATER SUPPLY SCHEME | SM/15655 | New | PAYMENT FOR WBSEDCL |  |  | BILL/00854/2023-2024 | BP-2024-25-56 | 07/06/2024 | 07/06/2024 | WBSEDCL | 51.83 | 0 | 0 | 0
3 | DARJEELING | Mirik | Neorakhola W/S & Mtc.Div. | PATONG TEA GARDEN PIPED WATER SUPPLY SCHEME | SM/15655 | New | SURFACE WATER BASED PATONG TEA GARDEN PIPED WATER SUPPLY SCHEME TO ACCOMODATE FUNCTIONAL HOUSEHOLD TAP CONNECTION IN MIRIK BLOCK. |  |  | ORD/000016/2023-2024 | 116/NKWSMD | 28/04/2023 | 03/08/2026 | SRINIWAS AGARWAL | 677.35 | 0 | 0 | 90
Total | [13 empty] | 733.47 | 0 | 0