## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | DARJEELING | Rangli Rangliot | Neorakhola W/S & Mtc.Div. | KOLBONG KHASMAHAL PWSS | SM/15840 | New | WATER SUPPLY SCHEME FOR KOLBONG KHASMAHAL PIPED WATER SUPPLY SCHEME UNDER BLOCK : RANGLI RANGLIOT, DISTRICT: DARJEELING. |  |  | ORD/000045/2023-2024 | 189/NKWSMD | 04/05/2023 | 14/06/2025 | SRINIWAS AGARWAL | 212.21 | 158.9 | 74.88 | 100
2 | DARJEELING | Rangli Rangliot | Neorakhola W/S & Mtc.Div. | KOLBONG KHASMAHAL PWSS | SM/15840 | New | Material Requisition To Resource Division |  |  | RTOR000037/2023-2024 | 324/NKWSMD | 24/05/2023 | 24/05/2023 | Resource Division | 0.88 | 0 | 0 | 0
Total | [13 empty] | 213.09 | 158.9 | 74.57