## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | DARJEELING | Darjeeling Pulbazar | Neorakhola W/S & Mtc.Div. | LAMAGAON PIPED WATER SUPPLY SCHEME. | SM/15868 | New | Material Requisition To Resource Division |  |  | RTOR000023/2023-2024 | 242/NKWSMD | 12/05/2023 | 12/05/2023 | Resource Division | 3.87 | 0 | 0 | 0
2 | DARJEELING | Darjeeling Pulbazar | Neorakhola W/S & Mtc.Div. | LAMAGAON PIPED WATER SUPPLY SCHEME. | SM/15868 | New | SOIL TESTING FOR WATER STORAGE STRUCTURE (1) BIJANBARI PIPED WATER SUPPLY SCHEME.(2) DANGIA PIPED WATER SUPPLY SCHEME (3) NAMLA BUSTY PIPED WATER SUPPLY SCHEME (4) LAMAGAON PIPED WATER SUPPLY SCHEME (5) PUBONG KHASHMAHAL PIPED WATER SUPPLY SCHEME (6) HUM TUKDAH KHASMAHAL PWSS (7) MANEDARA PIPED WATER SUPPLY SCHEME (8) SORIANG KHASMAHAL & TAKLING BUSTY Piped Water Supply Scheme (9) TODAY TANGTA KHASMAHAL PWSS (10) UPPER FAGU PIPED WATER SUPPLY SCHEME. (11) PATEN GODAK KHASMAHAL PWSS (12) SAMSING MIDDLE & UPPER PIPED WATER SUPPLY SCHEME. (13) LODHAMA PIPED WATER SUPPLY SCHEME. (14) TAKLING KHASMAHAL & CHOTA MANGWA Piped Water Supply Scheme FOR PWSS, DARJEELING, GTA |  |  | BILL/00194/2023-2024 | BP-2023-24-155 | 23/08/2023 | 23/08/2023 | JALPAIGURI GOVERNMENT ENGINEERING COLLEGE | 8.4 | 0 | 0 | 0
3 | DARJEELING | Darjeeling Pulbazar | Neorakhola W/S & Mtc.Div. | LAMAGAON PIPED WATER SUPPLY SCHEME. | SM/15868 | New | WATER SUPPLY SCHEME FOR LAMAGAON PIPED WATER SUPPLY SCHEME IN PULBAZAR BLOCK UNDER DARJEELING DISTRICT. |  |  | ORD/000038/2023-2024 | 221/NKWSMD | 10/05/2023 | 06/10/2024 | TULSI NIROLA | 679.13 | 657.81 | 96.86 | 50
4 | DARJEELING | Darjeeling Pulbazar | Neorakhola W/S & Mtc.Div. | LAMAGAON PIPED WATER SUPPLY SCHEME. | SM/15868 | New | Additional Estimate for Construction of platform at Lamagaon Piped Water Supply Scheme under Pulbazar Bijanbari Block, PHED, Darjeeling Division, GTA. |  |  | ORD/000099/2024-2025 | 976/NKWSMD | 18/06/2024 | 17/08/2024 | TULSI NIROLA | 32.99 | 32.35 | 98.04 | 100
5 | DARJEELING | Darjeeling Pulbazar | Neorakhola W/S & Mtc.Div. | LAMAGAON PIPED WATER SUPPLY SCHEME. | SM/15868 | New | Providing Functional Household tap Connection under JJM & JSP Programme for Balance Household at Jhepi & Gurdung in Lamagaon under Darjeeling Division : PHED-GTA. |  |  | ORD/000150/2023-2024 | 878/NKWSMD | 03/08/2023 | 18/07/2024 | NARAYAN SUBBA | 33.7 | 0 | 0 | 100
Total | [13 empty] | 758.09 | 690.16 | 91.04