## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | DARJEELING | Darjeeling Pulbazar | Neorakhola W/S & Mtc.Div. | GOKE PIPED WATER SUPPLY SCHEME. | SM/15873 | New | Material Requisition To Resource Division |  |  | RTOR000089/2023-2024 | 813/NKWSMD | 24/07/2023 | 24/07/2023 | Resource Division | 6.67 | 0 | 0 | 0
2 | DARJEELING | Darjeeling Pulbazar | Neorakhola W/S & Mtc.Div. | GOKE PIPED WATER SUPPLY SCHEME. | SM/15873 | New | ADDITIONAL WORK FOR PIPED WATER SUPPLY SCHEME FOR GOKE UNDER PULL BIJANIARI BLOCK DARJEELING DIVISION, PHED TO ACCOMMODATE FHTC IN PULL BIJANBARI BLOCK |  |  | ORD/000140/2024-2025 | 2331/NKWSMD | 17/12/2024 | 15/06/2025 | MS. SURYA I PVT. LTD COMPANY | 66.7 | 0 | 0 | 0
3 | DARJEELING | Darjeeling Pulbazar | Neorakhola W/S & Mtc.Div. | GOKE PIPED WATER SUPPLY SCHEME. | SM/15873 | New | WATER SUPPLY SCHEME FOR GOKE-I PIPED WATER SUPPLY SCHEME IN PULBAZAR BLOCK UNDER DARJEELING DISTRICT |  |  | ORD/000226/2023-2024 | 1293/NKWSMD | 17/10/2023 | 16/10/2024 | VAISHNO CONSTRUCTION | 839.28 | 0 | 0 | 68
Total | [13 empty] | 912.65 | 0 | 0