## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | DARJEELING | Rangli Rangliot | Neorakhola W/S & Mtc.Div. | PUMONG TEA GARDEN PIPED WATER SUPPLY SCHEME. | SM/15876 | New | Material Requisition To Resource Division |  |  | RTOR000075/2023-2024 | 764/NKWSMD | 19/07/2023 | 19/07/2023 | Resource Division | 7.38 | 0 | 0 | 0
2 | DARJEELING | Rangli Rangliot | Neorakhola W/S & Mtc.Div. | PUMONG TEA GARDEN PIPED WATER SUPPLY SCHEME. | SM/15876 | New | WATER SUPPLY SCHEME FOR PUMONG TEA GARDEN PIPED WATER SUPPLY SCHEME RANGLI RANGLIOT BLOCK UNDER DARJEELING DISTRICT. |  |  | ORD/000083/2023-2024 | 682/NKWSMD | 12/07/2023 | 09/10/2024 | RAMESH AGARWAL | 701.65 | 0 | 0 | 50
3 | DARJEELING | Rangli Rangliot | Neorakhola W/S & Mtc.Div. | PUMONG TEA GARDEN PIPED WATER SUPPLY SCHEME. | SM/15876 | New | Additional estimate for water supply scheme for Pumong Tea Garden piped water supply scheme in rangli-rangliot Block under Darjeeling District. |  |  | ORD/000019/2024-2025 | 983/NKWSMD | 18/06/2024 | 17/08/2024 | RAMESH AGARWAL | 48.79 | 0 | 0 | 100
Total | [13 empty] | 757.82 | 0 | 0