## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | DARJEELING | Darjeeling Pulbazar | Neorakhola W/S & Mtc.Div. | CHEWARI BOTAY PIPED WATER SUPPLY SCHEME. | SM/15877 | New | Material Requisition To Resource Division |  |  | RTOR000040/2023-2024 | 327/NKWSMD | 24/05/2023 | 24/05/2023 | Resource Division | 0.21 | 0 | 0 | 0
2 | DARJEELING | Darjeeling Pulbazar | Neorakhola W/S & Mtc.Div. | CHEWARI BOTAY PIPED WATER SUPPLY SCHEME. | SM/15877 | New | (Continuation) Engagement of 01 (One) number Computer Operator (Graduate with Certificate in Computer Application) for the works related to Jal Jeevan Mission /Jal Swapno at the Office of the Executive Engineer, Neorakhola Water Supply & Maintenance Division, Public Health Engineering Directorate, Kalimpong from 01.06.2024 to 31.07.2024 | Assistant Engineer II | Junior Engineer I | ORD/000051/2024-2025 | 385/NKWSMD | 31/05/2024 | 31/07/2024 | YAMA CONSTRUCTIONS LLP | 0.39 | 0 | 0 | 100
3 | DARJEELING | Darjeeling Pulbazar | Neorakhola W/S & Mtc.Div. | CHEWARI BOTAY PIPED WATER SUPPLY SCHEME. | SM/15877 | New | WATER SUPPLY SCHEME FOR CHEWARIBOTAY PIPED WATER SUPPLY SCHEME IN DARJEELING PULBAZAR BLOCK UNDER DARJEELING DISTRICT. |  |  | ORD/000048/2023-2024 | 261/NKWSMD | 15/05/2023 | 12/09/2023 | NIMA SHERPA | 132.89 | 0 | 0 | 100
Total | [13 empty] | 133.5 | 0 | 0