## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | DARJEELING | Darjeeling Pulbazar | Neorakhola W/S & Mtc.Div. | RELLING PIPED WATER SUPPLY SCHEME. | SM/15879 | New | Material Requisition To Resource Division |  |  | RTOR000051/2023-2024 | 446/NKWSMD | 07/06/2023 | 07/06/2023 | Resource Division | 4.21 | 0 | 0 | 0
2 | DARJEELING | Darjeeling Pulbazar | Neorakhola W/S & Mtc.Div. | RELLING PIPED WATER SUPPLY SCHEME. | SM/15879 | New | Laying of additional pipeline for Augmentation scheme for Bijanbari Bazar under Darjeeling Division: PHED-GTA. | Assistant Engineer 1 | Sub-Assistant Engineer | ORD/000149/2023-2024 | 877/NKWSMD | 03/08/2023 | 02/10/2023 | TULSI NIROLA | 40.01 | 0 | 0 | 50
3 | DARJEELING | Darjeeling Pulbazar | Neorakhola W/S & Mtc.Div. | RELLING PIPED WATER SUPPLY SCHEME. | SM/15879 | New | WATER SUPPLY SCHEME FOR RELLING PIPED WATER SUPPLY SCHEME IN DARJEELING PULBAZAR BLOCK UNDER DARJEELING DISTRICT. |  |  | ORD/000061/2023-2024 | 426/NKWSMD | 06/06/2023 | 05/06/2024 | NIMA SHERPA | 857.26 | 0 | 0 | 55
Total | [13 empty] | 901.47 | 0 | 0