## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | DARJEELING | Darjeeling Pulbazar | Neorakhola W/S & Mtc.Div. | CHAINPURAY PIPED WATER SUPPLY SCHEME | SM/15881 | New | WATER SUPPLY SCHEME FOR CHAINPURAY PIPED WATER SUPPLY SUPPLY IN DARJEELING PULBAZAR BLOCK UNDER DARJEELING DISTRICT. |  |  | ORD/000081/2023-2024 | 680/NKWSMD | 12/07/2023 | 16/09/2025 | VAISHNO CONSTRUCTION | 80.25 | 44.06 | 54.9 | 100
2 | DARJEELING | Darjeeling Pulbazar | Neorakhola W/S & Mtc.Div. | CHAINPURAY PIPED WATER SUPPLY SCHEME | SM/15881 | New | Material Requisition To Resource Division |  |  | RTOR000068/2023-2024 | 755/NKWSMD | 19/07/2023 | 19/07/2023 | Resource Division | 0.86 | 0 | 0 | 0
Total | [13 empty] | 81.11 | 44.06 | 54.31