## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | DARJEELING | Rangli Rangliot | Neorakhola W/S & Mtc.Div. | RESHOP BAZAR PIPED WATER SUPPLY SCHEME | SM/15882 | New | WATER SUPPLY SCHEME FOR RESHOP BAZAR PIPED WATER SUPPLY SCHEME RANGLI RANGLIOT BLOCK UNDER DARJEELING DISTRICT. | Assistant Engineer | Sub-Assistant Engineer | ORD/000024/2023-2024 | 123/NKWSMD | 28/04/2023 | 23/12/2024 | VAISHNO CONSTRUCTION | 416.96 | 160.21 | 38.42 | 100
2 | DARJEELING | Rangli Rangliot | Neorakhola W/S & Mtc.Div. | RESHOP BAZAR PIPED WATER SUPPLY SCHEME | SM/15882 | New | Material Requisition To Resource Division |  |  | RTOR000016/2023-2024 | 214/NKWSMD | 10/05/2023 | 10/05/2023 | Resource Division | 1.11 | 0 | 0 | 0
Total | [13 empty] | 418.07 | 160.21 | 38.32