## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | DARJEELING | Darjeeling Pulbazar | Neorakhola W/S & Mtc.Div. | HATTA PIPED WATER SUPPLY SCHEME. | SM/15883 | New | Material Requisition To Resource Division |  |  | RTOR000047/2023-2024 | 442/NKWSMD | 07/06/2023 |  | Resource Division | 0.83 | 0 | 0 | 0
2 | DARJEELING | Darjeeling Pulbazar | Neorakhola W/S & Mtc.Div. | HATTA PIPED WATER SUPPLY SCHEME. | SM/15883 | New | Water Supply Scheme For Hatta Piped Water Supply Scheme in Darjeeling Pulbazar Block under Darjeeling District. |  |  | ORD/000058/2023-2024 | 413/NKWSMD | 05/06/2023 | 02/12/2023 | SAGARMATHA CONSTRUCTION CO. | 278.82 | 0 | 0 | 65
Total | [13 empty] | 279.65 | 0 | 0