## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | DARJEELING | Kurseong | Neorakhola W/S & Mtc.Div. | PIPED WATER SUPPLY SCHEME FOR JAMADARBHITA KHASMAHAL(PART-1) IN KURSEONG BLOCK UNDER DARJEELING DISTRICT. | SM/15884 | New | Material Requisition To Resource Division |  |  | RTOR000086/2023-2024 | 797/NKWSMD | 20/07/2023 | 20/07/2023 | Resource Division | 3.43 | 0 | 0 | 0
2 | DARJEELING | Kurseong | Neorakhola W/S & Mtc.Div. | PIPED WATER SUPPLY SCHEME FOR JAMADARBHITA KHASMAHAL(PART-1) IN KURSEONG BLOCK UNDER DARJEELING DISTRICT. | SM/15884 | New | WATER SUPPLY SCHEME FOR JAMADAR BHITA KHASMAHAL (PART-1 & 2) PIPED WATER SUPPLY SCHEME IN KURSEONG, UNDER DARJEELING DISTRICT. |  |  | ORD/000094/2023-2024 | 718/NKWSMD | 18/07/2023 | 13/05/2025 | GARGO TRADERS | 976.84 | 0 | 0 | 70
3 | DARJEELING | Kurseong | Neorakhola W/S & Mtc.Div. | PIPED WATER SUPPLY SCHEME FOR JAMADARBHITA KHASMAHAL(PART-1) IN KURSEONG BLOCK UNDER DARJEELING DISTRICT. | SM/15884 | New | ADDITIONAL WORK FOR PIPED WATER SUPPLY SCHEME FOR JAMADARBHITTA KHASMAHAL (PART-1 & 2) IN KURSEONG BLOCK UNDER DARJEELING DISTRICT. |  |  | ORD/000024/2025-2026 | 592/NKWSMD | 29/04/2025 | 26/10/2025 | GARGO TRADERS | 45.62 | 0 | 0 | 0
Total | [13 empty] | 1025.89 | 0 | 0