## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | DARJEELING | Rangli Rangliot | Neorakhola W/S & Mtc.Div. | MANEDARA PIPED WATER SUPPLY SCHEME. | SM/15885 | New | SOIL TESTING FOR WATER STORAGE STRUCTURE (1) BIJANBARI PIPED WATER SUPPLY SCHEME.(2) DANGIA PIPED WATER SUPPLY SCHEME (3) NAMLA BUSTY PIPED WATER SUPPLY SCHEME (4) LAMAGAON PIPED WATER SUPPLY SCHEME (5) PUBONG KHASHMAHAL PIPED WATER SUPPLY SCHEME (6) HUM TUKDAH KHASMAHAL PWSS (7) MANEDARA PIPED WATER SUPPLY SCHEME (8) SORIANG KHASMAHAL & TAKLING BUSTY Piped Water Supply Scheme (9) TODAY TANGTA KHASMAHAL PWSS (10) UPPER FAGU PIPED WATER SUPPLY SCHEME. (11) PATEN GODAK KHASMAHAL PWSS (12) SAMSING MIDDLE & UPPER PIPED WATER SUPPLY SCHEME. (13) LODHAMA PIPED WATER SUPPLY SCHEME. (14) TAKLING KHASMAHAL & CHOTA MANGWA Piped Water Supply Scheme FOR PWSS, DARJEELING, GTA |  |  | BILL/00194/2023-2024 | BP-2023-24-155 | 23/08/2023 | 23/08/2023 | JALPAIGURI GOVERNMENT ENGINEERING COLLEGE | 8.4 | 0 | 0 | 0
2 | DARJEELING | Rangli Rangliot | Neorakhola W/S & Mtc.Div. | MANEDARA PIPED WATER SUPPLY SCHEME. | SM/15885 | New | WATER SUPPLY SCHEME FOR MANEDARA PIPED WATER SUPPLY SCHEME RANGLI RANGLIOT BLOCK UNDER DARJEELING DISTRICT. |  |  | ORD/000063/2023-2024 | 437/NKWSMD | 07/06/2023 | 27/04/2025 | ALLIED INSTRUMENTS | 413.06 | 268.41 | 64.98 | 50
3 | DARJEELING | Rangli Rangliot | Neorakhola W/S & Mtc.Div. | MANEDARA PIPED WATER SUPPLY SCHEME. | SM/15885 | New | Additional estimate for water supply scheme for Manedara piped water supply scheme in Rangli-Rangliot Block under Darjeeling District. (SM/15885) |  |  | ORD/000017/2024-2025 | 981/NKWSMD | 18/06/2024 | 17/08/2024 | ALLIED INSTRUMENTS | 13.06 | 12.1 | 92.65 | 100
4 | DARJEELING | Rangli Rangliot | Neorakhola W/S & Mtc.Div. | MANEDARA PIPED WATER SUPPLY SCHEME. | SM/15885 | New | PROPOSED PUMPING BASED PIPED WATER SUPPLY SCHEME FOR RAMBI BAZAR DIF UNDER TEESTA G.P, BLOCK : KALIMPONG - I, DISTRICT:KALIMPONG |  |  | ORD/000322/2022-2023 | 2652/NKWSMD | 28/02/2023 | 25/10/2024 | KAMAKHAYA CONSTRUCTION | 179.69 | 2.14 | 1.19 | 80
5 | DARJEELING | Rangli Rangliot | Neorakhola W/S & Mtc.Div. | MANEDARA PIPED WATER SUPPLY SCHEME. | SM/15885 | New | Augmentation with new source with laying of HDPE pipes for Soring Khasmahal Piped Water Supply Scheme under Rangli Rangliot Block District Darjeeling. |  |  | ORD/000323/2023-2024 | 720/NKWSMD | 29/03/2024 | 01/01/2025 | SRINIWAS AGARWAL | 22.64 | 0 | 0 | 100
Total | [13 empty] | 636.85 | 282.65 | 44.38