## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | DARJEELING | Rangli Rangliot | Neorakhola W/S & Mtc.Div. | BARA MUNGWA PIPED WATER SUPPLY SCHEME | SM/15893 | New | Additional estimate for water supply scheme for Bara Mungwa piped water supply scheme in Rangli-Rangliot Block under Darjeeling District. |  |  | ORD/000016/2024-2025 | 980/NKWSMD | 18/06/2024 | 17/08/2024 | GARGO TRADERS | 12.72 | 0 | 0 | 100
2 | DARJEELING | Rangli Rangliot | Neorakhola W/S & Mtc.Div. | BARA MUNGWA PIPED WATER SUPPLY SCHEME | SM/15893 | New | PROPOSED PUMPING BASED PIPED WATER SUPPLY SCHEME FOR RAMBI BAZAR DIF UNDER TEESTA G.P, BLOCK : KALIMPONG - I, DISTRICT:KALIMPONG |  |  | ORD/000322/2022-2023 | 2652/NKWSMD | 28/02/2023 | 25/10/2024 | KAMAKHAYA CONSTRUCTION | 179.69 | 2.21 | 1.23 | 80
Total | [13 empty] | 192.41 | 2.21 | 1.15