## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | DARJEELING | Matigara | Neorakhola W/S & Mtc.Div. | PWS Scheme for Sevok Hill Forest area under Kurseong Block. | SM/15895 | New | Material Requisition To Resource Division |  |  | RTOR000056/2023-2024 | 441/NKWSMD | 07/06/2023 | 07/06/2023 | Resource Division | 1.15 | 0 | 0 | 0
2 | DARJEELING | Matigara | Neorakhola W/S & Mtc.Div. | PWS Scheme for Sevok Hill Forest area under Kurseong Block. | SM/15895 | New | WATER SUPPLY SCHEME FOR SEVOKE HILL FOREST PIPED WATER SUPPLY SCHEME IN KURSEONG BLOCK UNDER DARJEELING DISTRICT [SM - 15895] |  |  | BILL/00231/2024-2025 | BP-2024-25-234 | 03/09/2024 | 03/09/2024 | WBSEDCL | 4.17 | 0 | 0 | 0
3 | DARJEELING | Matigara | Neorakhola W/S & Mtc.Div. | PWS Scheme for Sevok Hill Forest area under Kurseong Block. | SM/15895 | New | WATER SUPPLY SCHEME FOR SEVOKE HILL FOREST PIPED WATER SUPPLY SCHEME IN KURSEONG BLOCK UNDER DARJEELING DISTRICT [SM NO - 15895] |  |  | BILL/00232/2024-2025 | BP-2024-25-235 | 03/09/2024 | 03/09/2024 | WBSEDCL | 4.17 | 0 | 0 | 0
4 | DARJEELING | Matigara | Neorakhola W/S & Mtc.Div. | PWS Scheme for Sevok Hill Forest area under Kurseong Block. | SM/15895 | New | WATER SUPPLY SCHEME FOR SEVOK HILL FOREST PIPED WATER SUPPLY SCHEME IN KURSEONG BLOCK UNDER DARJEELING DISTRICT. |  |  | ORD/000062/2023-2024 | 434/NKWSMD | 06/06/2023 | 31/01/2025 | SRINIWAS AGARWAL | 216.18 | 122.72 | 56.77 | 85
Total | [13 empty] | 225.67 | 122.72 | 54.38